## Summary
Metric | Count | Bug IDs | Notes
Total bug IDs in BUG_TEMPLATE.md | 51 | BUG-001..BUG-035, BUG-036..BUG-049, plus BUG-042-A/B/C | Sub-bugs counted under BUG-042 row.
Closed / smoke passed (May-2026 sprint) | 24 | BUG-011, BUG-016, BUG-024, BUG-028, BUG-029, BUG-030, BUG-031, BUG-032, BUG-033, BUG-034, BUG-035, BUG-036, BUG-037, BUG-042 (parent), BUG-042-A, BUG-042-B, BUG-042-C, BUG-043, BUG-044, BUG-045, BUG-046, BUG-047, BUG-048, BUG-049 | Three-batch closure on 2026-05-12: Tier-1 (7) + BE-resolved batch (10) + plan-stage batch (3).
Closed / terminal by tracker | 2 | BUG-005, BUG-008 | Closed in tracker (not a business req / already working).
Implemented + QA passed / smoke pending | 0 | — | Empty.
Docs-code mismatch | 0 | — | Empty.
Code present / formal docs needed (legacy Apr-2026) | 19 | BUG-001..BUG-010, BUG-012..BUG-015, BUG-017..BUG-023, BUG-025..BUG-027 | Apr-2026 fixes recorded inside BUG_TEMPLATE; code present. See Closed_Legacy sheet.
Implementation plan ready | 0 | — | Empty (BUG-030/031/033 all closed).
Impact analysis done — plan next | 1 | BUG-038 | CRM autofill; needs implementation plan.
Ready for pre-implementation code gate | 0 | — | Empty.
Intake only | 2 | BUG-040, BUG-041 | Awaiting owner spec.
Needs backend confirmation | 1 | BUG-039 | Audit Report — only remaining backend ask.
Open — backend bug (FE untouched) | 0 | — | Empty.
Parked under another CR | 0 | — | Empty.
Parked pending reproduction | 0 | — | Empty.
Final-docs sweep candidates (deferred) | 2 | BUG-042-C, BUG-048 | Owner-approved baseline revisions; sweep not yet performed.
Tracker row flips pending in BUG_TEMPLATE.md | 24 | All 24 May-2026 closures | Tracker-keeper action — agent does not edit BUG_TEMPLATE.md per strict rules.
Status (Option B, regenerated 2026-05-12) | Count | Closure Type | Bug IDs
Closed | 1 | Already working | BUG-008
Closed | 3 | Final-doc swept | BUG-025, BUG-026, BUG-027
Closed | 1 | Not a business requirement | BUG-005
Closed | 23 | Smoke Passed 2026-05-12 | BUG-011, BUG-016, BUG-024, BUG-028, BUG-029, BUG-032, BUG-034, BUG-035, BUG-036, BUG-037, BUG-042-A, BUG-042-B, BUG-042-C, BUG-043, BUG-044, BUG-045, BUG-046, BUG-047, BUG-048, BUG-049, BUG-030, BUG-031, BUG-033
Closed | 19 | Verified 2026-05-12 (retro) | BUG-001, BUG-002, BUG-003, BUG-004, BUG-006, BUG-007, BUG-009, BUG-010, BUG-012, BUG-013, BUG-014, BUG-015, BUG-017, BUG-018, BUG-019, BUG-020, BUG-021, BUG-022, BUG-023
(blank) | 1 | (blank) | BUG-042 (parent)
Open | 4 | Intake Created | BUG-038, BUG-039, BUG-040, BUG-041
TOTAL | 52

## Master Bug Register
Bug ID | Title | Status | Closure Type | Current Status | Latest Stage | Latest Artifact | Resolution Category | What is Completed | What Remains | Next Action | Owner Action Needed | Backend Action Needed | Smoke Status | Final-Docs Sweep Needed | Relationships | Notes
BUG-011 | Scan & Order Confirm — HTTP 500 / 404 | Closed | Smoke Passed 2026-05-12 | Closed / smoke passed | Smoke signoff (2026-05-12) | /app/memory/bugs/BUG_011_SMOKE_SIGNOFF.md | Backend fix (shared root cause with BUG-037) | Backend fix delivered + owner-verified | Tracker row flip | Owner: tracker flip | No | No | Passed (2026-05-12) | No | Shared root cause with BUG-037 | Backend fixed BadMethodCallException; FE untouched.
BUG-016 | Delivery Payload Sent on Non-Delivery Order Types | Closed | Smoke Passed 2026-05-12 | Closed / smoke passed | Smoke signoff (2026-05-12) | /app/memory/bugs/BUG_016_SMOKE_SIGNOFF.md | FE workaround (Apr-2026) + Backend isset() guard | FE workaround intact + BE guard delivered + owner-verified | Tracker row flip | Owner: tracker flip | No | No | Passed (2026-05-12) | No | — | Closed in second batch on 2026-05-12.
BUG-024 | Mark Order Ready — backend food_status cascade missing | Closed | Smoke Passed 2026-05-12 | Closed / smoke passed | Smoke signoff (2026-05-12) | /app/memory/bugs/BUG_024_SMOKE_SIGNOFF.md | Backend fix (cascade + event name) | Backend fix delivered + owner-verified | Tracker row flip | Owner: tracker flip | No | No | Passed (2026-05-12) | No | Cancelled-item visibility (BUG-025) now consistent | FE intentionally untouched.
BUG-028 | Service Charge Auto-Added even when toggle Off | Closed | Smoke Passed 2026-05-12 | Closed / smoke passed | Smoke signoff (2026-05-12) | /app/memory/bugs/BUG_028_SMOKE_SIGNOFF.md | FE fix (CollectPaymentPanel + OrderEntry) | Implementation + QA + smoke 5/5 PASS | Tracker row flip | Owner: tracker flip | No | No | Passed (5/5, 2026-05-12) | No | — | Tier-1 closure.
BUG-029 | Prepaid Order — POS Returns to Previous Order's Edit Screen | Closed | Smoke Passed 2026-05-12 | Closed / smoke passed | Smoke signoff (2026-05-12) | /app/memory/bugs/BUG_029_SMOKE_SIGNOFF.md | FE fix (OrderEntry reset nonce) | Implementation + QA + smoke 5/5 PASS | Tracker row flip | Owner: tracker flip | No | No | Passed (5/5, 2026-05-12) | No | — | Tier-1 closure.
BUG-032 | Backend Order ID shown instead of Restaurant Order ID | Closed | Smoke Passed 2026-05-12 | Closed / smoke passed | Smoke signoff (2026-05-12) | /app/memory/bugs/BUG_032_SMOKE_SIGNOFF.md | FE fix (OrderEntry + CollectPaymentPanel) | Implementation + QA + smoke 5/5 PASS | Tracker row flip | Owner: tracker flip | No | No | Passed (5/5, 2026-05-12) | No | — | Tier-1 closure.
BUG-034 | Inconsistent Notification Tone When Placing/Serving Orders | Closed | Smoke Passed 2026-05-12 | Closed / smoke passed | Smoke signoff (2026-05-12) | /app/memory/bugs/BUG_034_SMOKE_SIGNOFF.md | FE fix (notification tone alignment) | Implementation + QA + smoke 5/5 PASS | Tracker row flip | Owner: tracker flip | No | No | Passed (5/5, 2026-05-12) | No | Cross-ref BUG-033 (plan-only) | Tier-1 closure.
BUG-035 | Dynamic Price Feature Missing in New POS | Closed | Smoke Passed 2026-05-12 | Closed / smoke passed | Smoke signoff (2026-05-12) | /app/memory/bugs/BUG_035_SMOKE_SIGNOFF.md | FE fix (OrderEntry + ItemCustomizationModal) | Implementation + QA + smoke 7/7 PASS | Tracker row flip | Owner: tracker flip | No | No | Passed (7/7, 2026-05-12) | No | — | Tier-1 closure.
BUG-036 | PG-Paid Scan Order Stays on Dashboard After Mark-Served | Closed | Smoke Passed 2026-05-12 | Closed / smoke passed | Smoke signoff (2026-05-12) | /app/memory/bugs/BUG_036_SMOKE_SIGNOFF.md | Backend fix (BE-A canonical paymentType via CR-011) | Backend fix delivered + owner-verified | Tracker row flip + CR-011 close | Owner: tracker flip (+ close CR-011) | No | No | Passed (2026-05-12) | No | Tracked under CR-011 | FE untouched.
BUG-037 | Scan & Order Accept fails when default = 'Delivered' | Closed | Smoke Passed 2026-05-12 | Closed / smoke passed | Smoke signoff (2026-05-12) | /app/memory/bugs/BUG_037_SMOKE_SIGNOFF.md | Backend fix + FE constants alignment | Backend fix delivered + owner-verified | Tracker row flip | Owner: tracker flip | No | No | Passed (2026-05-12) | No | Shared root cause with BUG-011 | F_ORDER_STATUS_API constants verified consistent.
BUG-042 (parent) | Hold Order — Payment Collection Fails With UPI | Closed | Smoke Passed 2026-05-12 | Closed / smoke passed | Smoke signoff (2026-05-12) | /app/memory/bugs/BUG_042_SMOKE_SIGNOFF.md | Backend fix + sub-bugs A/B/C | Backend fix delivered + all sub-bugs closed + owner-verified | Tracker row flip | Owner: tracker flip | No | No | Passed (2026-05-12) | No | Split into A/B/C — all 3 closed | Parent UPI failure root cause resolved by backend.
BUG-042-A | Hold Collect Bill rail cleanup + row-level Collect disable | Closed | Smoke Passed 2026-05-12 | Closed / smoke passed | Smoke signoff (2026-05-12) | /app/memory/bugs/BUG_042_A_SMOKE_SIGNOFF.md | FE fix (4 files) | Implementation + 472/472 tests + smoke 10/10 PASS | Tracker row flip | Owner: tracker flip | No | No | Passed (10/10, 2026-05-12) | No | Sub-bug of BUG-042 parent | Tier-1 closure.
BUG-042-B | BILL_PAYMENT 'grand_amount' → 'grant_amount' payload rename | Closed | Smoke Passed 2026-05-12 | Closed / smoke passed | Smoke signoff | /app/memory/bugs/BUG_042_B_SMOKE_SIGNOFF.md | FE fix (orderTransform.js single-site rename) | Implementation + QA + smoke | Tracker row flip | Owner: tracker flip | No | No | Passed | No | Sub-bug of BUG-042 parent | Owner-confirmed preprod smoke.
BUG-042-C | Add f_order_status=9 (PayLater/Hold) to running terminal-clear | Closed | Smoke Passed 2026-05-12 | Closed / smoke passed | Smoke signoff | /app/memory/bugs/BUG_042_C_SMOKE_SIGNOFF.md | FE fix (socketHandlers.js) | Implementation + QA + smoke 7/7 PASS | Tracker row flip + final-docs sweep (deferred) | Owner: tracker flip | No | No | Passed | Yes — deferred per owner | Sub-bug of BUG-042 parent; supersedes BUG-044 PayLater/Hold half | Owner-approved baseline revision.
BUG-043 | Room Orders Report — wrongly shows Discount column / value | Closed | Smoke Passed 2026-05-12 | Closed / smoke passed | Smoke signoff (2026-05-12) | /app/memory/bugs/BUG_043_SMOKE_SIGNOFF.md | Superseded by BUG-048 calculation model | BUG-048 calculation model adopted + owner-verified | Tracker row flip | Owner: tracker flip | No | No | Passed (2026-05-12) | No | Superseded by BUG-048 | Closed in second batch on 2026-05-12.
BUG-044 | Free / Available Table Still Shows Old Order Items | Closed | Smoke Passed 2026-05-12 | Closed / smoke passed | Smoke signoff (2026-05-12) | /app/memory/bugs/BUG_044_SMOKE_SIGNOFF.md | Covered by BUG-042-C + BUG-049 | BUG-042-C + BUG-049 coverage owner-verified | Tracker row flip | Owner: tracker flip | No | No | Passed (2026-05-12) | No | Covered by BUG-042-C + BUG-049 | Closed in second batch on 2026-05-12.
BUG-045 | New Web/Scan popup actions + ₹0 line items | Closed | Smoke Passed 2026-05-12 | Closed / smoke passed | Smoke signoff | /app/memory/bugs/BUG_045_SMOKE_SIGNOFF.md | FE fix (ScanOrderPopOut + DashboardPage) | All 14 sub-defects (45a-45n) + 10 owner smoke checks PASS | Tracker row flip + PR push | Owner: tracker flip | No | No | Passed (10/10) | No | Independent | Sealed.
BUG-046 | Editable Delivery Charge Accepted But Not in Order Total | Closed | Smoke Passed 2026-05-12 | Closed / smoke passed | Smoke signoff (2026-05-12) | /app/memory/bugs/BUG_046_SMOKE_SIGNOFF.md | Owner-verified working end-to-end | Owner-verified | Tracker row flip | Owner: tracker flip | No | No | Passed (2026-05-12) | No | — | Closed in second batch on 2026-05-12.
BUG-047 | New-order notification shows '18 March' instead of outlet | Closed | Smoke Passed 2026-05-12 | Closed / smoke passed | Smoke signoff (2026-05-12) | /app/memory/bugs/BUG_047_SMOKE_SIGNOFF.md | Backend fix (FCM payload composition) | Backend fix delivered + owner-verified | Tracker row flip | Owner: tracker flip | No | No | Passed (2026-05-12) | No | — | FE untouched.
BUG-048 | Room Orders Report inflated total / phantom discount | Closed | Smoke Passed 2026-05-12 | Closed / smoke passed | Smoke signoff | /app/memory/bugs/BUG_048_SMOKE_SIGNOFF.md | FE fix (RoomRowCard + RoomOrdersReportPage) | Owner-locked calculation model; 7/7 smoke PASS | Tracker row flip + 3 cosmetic deferrals tracked separately | Owner: tracker flip | No | No | Passed (7/7) | Candidate — deferred | Supersedes BUG-043 | —
BUG-049 | PayLater Payment Leaves 'NA' On Available Table Card | Closed | Smoke Passed 2026-05-12 | Closed / smoke passed | Smoke signoff (2026-05-12) | /app/memory/bugs/BUG_049_SMOKE_SIGNOFF.md | FE fix (socketHandlers.js BUG-049 predicate) | Implementation + 15/15 tests + smoke 7/7 PASS | Tracker row flip | Owner: tracker flip | No | No | Passed (7/7, 2026-05-12) | No | Refines BUG-042-C; covers BUG-044 PayLater table-card half | Tier-1 closure.
BUG-005 | Print Bill Button Missing on Prepaid Orders | Closed | Not a business requirement | Closed / terminal by tracker | Terminal | BUG_TEMPLATE.md row | Closed: not a business requirement | None | None | None | No | No | n/a | No | — | Closed — not a business requirement.
BUG-008 | Online Order Confirm Not Working | Closed | Already working | Closed / terminal by tracker | Terminal | BUG_TEMPLATE.md row | Closed: already working | None | None | None | No | No | n/a | No | — | Closed — already working.
BUG-030 | Cancelled KOT Not Received After Item Cancellation | Closed | Smoke Passed 2026-05-12 | Closed / smoke passed | Smoke signoff (2026-05-12) | /app/memory/bugs/BUG_030_SMOKE_SIGNOFF.md | FE fix (per plan) | Implementation delivered + owner-verified | Tracker row flip | Owner: tracker flip | No | No | Passed (2026-05-12) | No | — | Closed in third batch on 2026-05-12.
BUG-031 | Out-of-Menu Order Item Not Added to Menu Management | Closed | Smoke Passed 2026-05-12 | Closed / smoke passed | Smoke signoff (2026-05-12) | /app/memory/bugs/BUG_031_SMOKE_SIGNOFF.md | FE fix (per plan) | Implementation delivered + owner-verified | Tracker row flip | Owner: tracker flip | No | No | Passed (2026-05-12) | No | — | Closed in third batch on 2026-05-12.
BUG-033 | Cancellation Notification Says 'Order Updated' | Closed | Smoke Passed 2026-05-12 | Closed / smoke passed | Smoke signoff (2026-05-12) | /app/memory/bugs/BUG_033_SMOKE_SIGNOFF.md | FE fix (per plan) | Implementation delivered + owner-verified | Tracker row flip | Owner: tracker flip | No | No | Passed (2026-05-12) | No | Cross-ref BUG-034 (closed) | Closed in third batch on 2026-05-12.
BUG-038 | Credit Payment — CRM autofill | Open | Intake Created | Impact analysis done — plan next | Impact analysis | /app/memory/bugs/BUG_038_CREDIT_CUSTOMER_CRM_AUTOFILL_IMPACT_ANALYSIS.md | Impact analysis on disk | Impact analysis | Implementation plan agent | Owner: approve plan when produced | Yes (approval) | No | n/a | No | — | Ready for plan agent.
BUG-039 | Delivery Order — Audit Detail shows Delivery Charge as Tax | Open | Intake Created | Needs backend confirmation | Backend pull | /app/memory/bugs/BACKEND_CONFIRMATION_PULL_BUG_037_039_042_047.md | FE column gap identified; BE composite-tax question open | Backend ask drafted | BE: send one audit-API row for delivery order; FE adds Delivery Charge column + CSV/PDF | Owner: chase backend | No | Yes (BE sample) | n/a | No | — | Only remaining backend ask.
BUG-040 | Audit Report Excel/CSV Export Format Must Follow Provided Format | Open | Intake Created | Intake only | Intake | /app/memory/BUG_TEMPLATE.md (L3389) | No code change | Intake on disk | Impact analysis → plan | Owner: confirm desired CSV/Excel export format | Yes (format spec) | No | n/a | No | Related to CR-001 export col-count backlog | Intake-only stage.
BUG-041 | Audit Report PDF Download — Mixed/Misaligned Rows | Open | Intake Created | Intake only | Intake | /app/memory/BUG_TEMPLATE.md (L3453) | No code change | Intake on disk | Impact analysis → plan | Owner: confirm PDF row layout scope | Yes (scope) | No | n/a | No | Sibling of BUG-040 | Intake-only stage.

## Closed_Legacy
Bug ID | Title | Status | Closure Type | Current Status | Latest Stage | Latest Artifact | Resolution Category | What is Completed | What Remains | Next Action | Owner Action Needed | Backend Action Needed | Smoke Status | Final-Docs Sweep Needed | Relationships | Notes
BUG-001 | Prepaid Auto Bill Print — Missing Tip and Discount | Closed | Verified 2026-05-12 (retro) | Code present / formal docs needed (legacy) | Apr-2026 fix in tracker | BUG_TEMPLATE.md row | Apr-2026 fix | Apr-2026 fix recorded in tracker; code present | Optional per-bug archive doc | None | No | No | Implicit | No | — | Fixed (Apr-2026). Tier-2 retro QA candidate (money path).
BUG-002 | Postpaid Collect Bill — Auto Bill Print Not Triggered | Closed | Verified 2026-05-12 (retro) | Code present / formal docs needed (legacy) | Apr-2026 fix in tracker | BUG_TEMPLATE.md row | Apr-2026 fix | Apr-2026 fix recorded; code present | Optional archive | None | No | No | Implicit | No | — | Fixed (Apr-2026). Tier-2 candidate (money path).
BUG-003 | Credit on Walk-in — Name Field Auto-Fills 'Walk-In' | Closed | Verified 2026-05-12 (retro) | Code present / formal docs needed (legacy) | Apr-2026 fix | BUG_TEMPLATE.md row | Apr-2026 fix | Apr-2026 fix recorded; code present | Optional archive | None | No | No | Implicit | No | — | Fixed (Apr-2026).
BUG-004 | Split Bill — Total Amount Wrong in Equally / By Person | Closed | Verified 2026-05-12 (retro) | Code present / formal docs needed (legacy) | Apr-2026 fix | BUG_TEMPLATE.md row | Apr-2026 fix | Apr-2026 fix recorded; code present | Optional archive | None | No | No | Implicit | No | — | Fixed (Apr-2026). Tier-2 candidate (money path).
BUG-006 | Service Charge Before Discount | Closed | Verified 2026-05-12 (retro) | Code present / formal docs needed (legacy) | Apr-2026 fix | BUG_TEMPLATE.md row | Apr-2026 fix | Apr-2026 fix recorded; code present | Optional archive | None | No | No | Implicit | No | — | Fixed (Apr-2026). Tier-2 candidate (money path).
BUG-007 | placeOrder Payload Missing Full delivery_address | Closed | Verified 2026-05-12 (retro) | Code present / formal docs needed (legacy) | Apr-2026 FE fix | BUG_TEMPLATE.md row | FE workaround (Apr-2026) | FE workaround; BE persistence pending | BE: persist delivery_address | Owner: chase BE | No | Yes (BE) | Implicit (FE) | No | — | FE side closed; BE persistence open.
BUG-009 | Rounding Off — Inverted Logic (₹1.06 → ₹2) | Closed | Verified 2026-05-12 (retro) | Code present / formal docs needed (legacy) | Apr-2026 fix | BUG_TEMPLATE.md row | Apr-2026 fix | Apr-2026 fix recorded; code present | Optional archive | None | No | No | Implicit | No | — | FIXED (Apr-2026). Tier-2 candidate (money path).
BUG-010 | Discount/Tip Fields — No Max Validation | Closed | Verified 2026-05-12 (retro) | Code present / formal docs needed (legacy) | Apr-2026 fix | BUG_TEMPLATE.md row | Apr-2026 fix | Apr-2026 fix recorded; code present | Optional archive | None | No | No | Implicit | No | — | FIXED (Apr-2026).
BUG-012 | Delivery Order Edit — Address Not Showing / Not Printing | Closed | Verified 2026-05-12 (retro) | Code present / formal docs needed (legacy) | Apr-2026 FE fix (print path) | BUG_TEMPLATE.md row | FE workaround (Apr-2026) | FE fix recorded; BE persistence pending | BE: persist edited address | Owner: chase BE | No | Yes (BE) | Implicit | No | — | FIXED (print path, Apr-2026).
BUG-013 | Service Charge Applied to Takeaway / Delivery | Closed | Verified 2026-05-12 (retro) | Code present / formal docs needed (legacy) | Apr-2026 fix | BUG_TEMPLATE.md row | Apr-2026 fix | Apr-2026 fix recorded; code present | Optional archive | None | No | No | Implicit | No | BUG-023 is print-payload residual | FIXED (Apr-2026). Tier-2 candidate (tax path).
BUG-014 | GST Not Applied on Tip Amount | Closed | Verified 2026-05-12 (retro) | Code present / formal docs needed (legacy) | Apr-2026 fix | BUG_TEMPLATE.md row | Apr-2026 fix | Apr-2026 fix recorded; code present | Optional archive | None | No | No | Implicit | No | — | Closed — confirmed working. Tier-2 candidate (tax path).
BUG-015 | Loyalty / Coupon / Wallet — Feature Flag Gating | Closed | Verified 2026-05-12 (retro) | Code present / formal docs needed (legacy) | Apr-2026 fix | BUG_TEMPLATE.md row | Apr-2026 fix | Apr-2026 fix recorded; code present | Optional archive | None | No | No | Implicit | No | — | FIXED (Apr-2026).
BUG-017 | Quantity Input — Amount Not Updating (Variants/Add-ons) | Closed | Verified 2026-05-12 (retro) | Code present / formal docs needed (legacy) | Apr-2026 fix | BUG_TEMPLATE.md row | Apr-2026 fix | Apr-2026 fix recorded; code present | Optional archive | None | No | No | Implicit | No | — | FIXED (Apr-2026).
BUG-018 | Complimentary Items (7 sub-steps) | Closed | Verified 2026-05-12 (retro) | Code present / formal docs needed (legacy) | Apr-2026 IMPLEMENTATION RECORD inline | BUG_TEMPLATE.md §IMPLEMENTATION RECORD (L1726) | Apr-2026 fix | Apr-2026 fix recorded; code present (7 sub-steps) | Optional archive | None | No | No | Implicit | No | BUG-021 is effectively 'Part 4' | FIXED (Apr-2026). Tier-2 candidate (money path).
BUG-019 | Scan / Re-engaged Delivery — Delivery Charge Not Mapped | Closed | Verified 2026-05-12 (retro) | Code present / formal docs needed (legacy) | Apr-2026 fix | BUG_TEMPLATE.md row | Apr-2026 fix | Apr-2026 fix recorded; predicate later rewritten by CR-008 D1-Gate | Optional archive | None | No | No | Implicit | No | Predicate superseded by CR-008 D1-Gate | FIXED (Apr-2026).
BUG-020 | Discount — Integer Rounding Instead of 2-Decimal | Closed | Verified 2026-05-12 (retro) | Code present / formal docs needed (legacy) | Apr-2026 fix | BUG_TEMPLATE.md row | Apr-2026 fix | Apr-2026 fix recorded; code present | Optional archive | None | No | No | Implicit | No | — | FIXED (Apr-2026). Tier-2 candidate (money path).
BUG-021 | Runtime-Marked Comp Item — Prints at Actual Price (postpaid) | Closed | Verified 2026-05-12 (retro) | Code present / formal docs needed (legacy) | Apr-2026 v2 fix | BUG_TEMPLATE.md row | Apr-2026 v2 fix | Apr-2026 v2 fix recorded; code present | Optional archive | None | No | No | Implicit | No | Effectively BUG-018 'Part 4' | FIXED (Apr-2026, v2). Tier-2 candidate (money path).
BUG-022 | Cancelled Item — Not Shown as Strikethrough in Collect Bill | Closed | Verified 2026-05-12 (retro) | Code present / formal docs needed (legacy) | Apr-2026 fix | BUG_TEMPLATE.md row | Apr-2026 fix | Apr-2026 fix recorded; code present | Optional archive | None | No | No | Implicit | No | — | FIXED (Apr-2026).
BUG-023 | Print Bill from Dashboard Card — SC in Print Payload for TA/Delivery | Closed | Verified 2026-05-12 (retro) | Code present / formal docs needed (legacy) | Apr-2026 re-fix | BUG_TEMPLATE.md §IMPLEMENTATION RECORD + §FOLLOW-UP | Apr-2026 re-fix | Apr-2026 re-fix QA-verified; code present | Optional archive | None | No | No | Implicit | No | Print-payload residual of BUG-013 | RE-OPENED → RE-FIXED → QA-VERIFIED. Tier-2 candidate.
BUG-025 | Cancelled Item Not in Order Card 'Served' Dropdown | Closed | Final-doc swept | Code present / formal docs needed (legacy) | Historical final-doc delta | FINAL_DOCS_SUMMARY.md §93 | Final-doc delta sweep | Code present; delta refresh applied | None | None | No | No | Implicit | Already swept (final delta) | — | Already swept via FINAL_DOCS_SUMMARY historical delta.
BUG-026 | Station Panel — Variant/Add-on aggregation | Closed | Final-doc swept | Code present / formal docs needed (legacy) | Historical final-doc delta | FINAL_DOCS_SUMMARY.md §93 | Final-doc delta sweep | Code present; variant/add-on/note signature split | None | None | No | No | Implicit | Already swept (final delta) | — | Already swept.
BUG-027 | Room Check-In — Advance payment method capture | Closed | Final-doc swept | Code present / formal docs needed (legacy) | Historical final-doc delta | FINAL_DOCS_SUMMARY.md §93 | Final-doc delta sweep | Code present; advance-payment method capture | None | None | No | No | Implicit | Already swept (final delta) | — | Already swept.

## Action Checklists
Type | Priority | Item | Related Bug(s) | Blocker For | Status | Owner / Assignee
Owner | P0 | Tracker keeper: flip 24 bugs to Closed in BUG_TEMPLATE.md (full list in Summary sheet) | 24 bugs | Final tracker hygiene | Open | Tracker keeper
Owner | P0 | Tracker keeper: close CR-011 (PG-paid scan order paymentType canonicalisation) | BUG-036 / CR-011 | CR hygiene | Open | Tracker keeper
Owner | P1 | Send BUG-039 backend ask — one audit-API row JSON for delivery order | BUG-039 | BUG-039 FE fix scope | Open | Owner → Backend team
Owner | P1 | Confirm BUG-040 desired CSV/Excel export format (attach sample or say 'match old POS') | BUG-040 | IA → plan → impl | Open | Owner
Owner | P1 | Confirm BUG-041 PDF row layout scope (alignment-only OR redesign) | BUG-041 | IA → plan → impl | Open | Owner
Owner | P1 | Approve BUG-038 plan agent (impact analysis already on disk) | BUG-038 | Plan → impl → QA → smoke | Open | Owner
Owner | P2 | Approve Tier-3 one-line rule in IMPLEMENTATION_AGENT_RULES.md: '6-artifact gate required before Closed flip' | Process | Future-proofing | Open | Owner
Owner | P3 | Approve a future final-docs sweep window for BUG-042-C (and optionally BUG-048) | BUG-042-C, BUG-048 | Baseline finalisation | Open | Owner
Owner | P3 | Decide whether to run Tier-2 retrospective QA of Apr-2026 legacy bugs (BUG-001..BUG-023) | Legacy 19 bugs | Legacy evidence trail | Open | Owner
Backend | P3 | Persist delivery_address round-trip | BUG-007, BUG-012 | Legacy full close | Open | Backend team
QA | P3 | BUG-048 deferred: real-discount Outstanding nuance verification when explicit discount_amount > 0 | BUG-048 | Cosmetic deferral closure | Open | QA
Owner | ✅ DONE 2026-05-12 | Owner smoke pass for 7 grey-zone bugs (Tier-1): BUG-042-A, BUG-049, BUG-028, BUG-029, BUG-032, BUG-034, BUG-035 | 7 bugs | — | Done | Owner
Owner | ✅ DONE 2026-05-12 | Owner verified second batch of 10 bugs: BUG-011, BUG-016, BUG-024, BUG-036, BUG-037, BUG-042 (parent), BUG-043, BUG-044, BUG-046, BUG-047 | 10 bugs | — | Done | Owner
Owner | ✅ DONE 2026-05-12 | Owner verified third batch of 3 bugs: BUG-030, BUG-031, BUG-033 (plan-stage bugs delivered + verified) | 3 bugs | — | Done | Owner
Backend | ✅ DONE 2026-05-12 | Backend fixes delivered: BUG-011, BUG-016 (isset guard), BUG-024 (cascade), BUG-036 (BE-A), BUG-037, BUG-042 (UPI), BUG-047 (FCM) | 7 bugs | — | Done | Backend team