## POS2.0 Validation Tracker
CR / Bucket | Manual Validation Task | Validation Type | Status
SECTION A — Older sprint (May 3 → May 6)
CR-001 | Validate All Orders Report status derivation shows correct status for Paid / Running / Cancelled / Hold / Credit orders. | Manual QA | Yet to test
CR-001 | Validate Audit Report filter pills work correctly and do not conflict with other report filters. | Manual QA | Yet to test
CR-001 | Validate SRM badge/display logic remains correct on Audit / All Orders reports. | Manual QA | Yet to test
CR-001 | Validate report export columns align correctly after CR-001 export alignment fix. | Manual QA | Yet to test
CR-003 | Validate Hold order actions: Collect Bill from Hold works correctly. | Manual QA | Yet to test
CR-003 | Validate Change Payment Method action works without affecting paid/unpaid logic. | Manual QA | Yet to test
CR-003 | Validate Mark Unpaid action works and status/report display updates correctly. | Manual QA | Yet to test
CR-004 | Validate Room Orders Report shows All / Paid / Unpaid pills correctly. | Manual QA | Yet to test
CR-004 | Validate Paid / Unpaid classification does not use balancePayment incorrectly and stays within intended room-report scope. | Manual QA | Yet to test
CR-004 | Validate Room Orders Report does not break Audit Report filters. | Regression | Yet to test
CR-004 | Validate Paid column appears between Total and Outstanding and Rent label is renamed to Total in the expanded card. | Manual QA | Yet to test
CR-004 | Validate Remove-from-Room action works on settled SRM rows and respects Mark Unpaid permission. | Manual QA | Yet to test
CR-004 | Validate cross-day in-house view shows multi-day in-house rooms with correct Paid column. | Manual QA | Yet to test
CR-005 | Validate PG Order ID and PG Amount columns show only when PG filter is active. | Manual QA | Yet to test
CR-005 | Validate PG columns render — safely when payment gateway values are missing. | Manual QA | Yet to test
CR-005 | Validate PG Status column remains hidden until backend snapshot_razorpay_status arrives. | Backend-blocked | Yet to test
CR-006 | Validate optional variation groups do not block Add to Cart; required single + required multi (min/max) gate Add to Cart correctly. | Manual QA | Yet to test
CR-006 | Validate multi-select variation pricing reflects all selected variants in cart and qty +/- updates price correctly. | Manual QA | Yet to test
CR-007 | Validate Order ID chip is visible on order cards and Print Bill button appears on dashboard cards and Order Entry header. | Manual QA | Yet to test
CR-007 | Validate Merge and Table-Shift options are hidden on prepaid orders. | Manual QA | Yet to test
CR-008 | Validate delivery charge is captured and applied once in totals/payload/print and delivery field is locked for prepaid orders. | Manual QA | Yet to test
CR-008 | Validate Stay-on-Order-Entry localStorage preference keeps Order Entry open after Collect Bill. | Manual QA | Yet to test
A0a | Validate cash_on_delivery payment method is masked as '—' in Audit table, OrderDetailSheet, CSV/PDF export, and filter dropdown. | Manual QA | Yet to test
A0b | Validate running-orders fetch uses canonical role_name='Manager' and user/waiter name fallback renders '—' safely when missing. | Manual QA | Yet to test
CR-013 | Validate tax math: SC-GST, Tip-GST, Delivery-GST flow on payloads; per-component CGST/SGST visible on Collect Bill; round-off applies only to Grand Total. | Manual QA | Yet to test
CR-013 | Validate Bean Me Up printed bill — Service Charge GST should appear only once (currently printed twice on receipt). | Manual QA | Yet to test
Hygiene | Validate test infra cleanup (test libraries, setup file, RAW-FIELD prod fallback, prepaid-merge-shift bug) does not regress. | Regression | Yet to test
Hygiene | Validate CR-001 CSV/PDF export of date-ranged tab data still works (column-count carry-over flagged as cosmetic backlog). | Manual QA | Yet to test
SECTION B — Current POS2 sprint (May 9 → May 11)
POS2-002 Phase 4 | Validate Web / Scan YTC pop-out appears on dashboard when a scan order arrives and Web platform counter increments by 1 (live retest after FU-01 fix). | Manual QA | Yet to test
POS2-002 Phase 1 | Validate Web / Scan order source (order_from) is mapped correctly across dashboard cards, lists, reports, and downstream payloads. | Manual QA | Yet to test
POS2-002 Phase 2 | Validate web order delivery charge field is LOCKED when delivery charge > 0. | Manual QA | Yet to test
POS2-002 Phase 2 | Validate web order delivery charge field is EDITABLE when delivery charge = 0. | Manual QA | Yet to test
POS2-002 Phase 2 | Validate POS / manual delivery charge behaviour is unchanged (editable unless prepaid). | Regression | Yet to test
POS2-002 Phase 3 | Validate dashboard header Platform dropdown (All / POS / Web / Scan) is visible after status chips and before search; default reads 'Platform: All'. | Manual QA | Yet to test
POS2-002 Phase 3 | Validate Platform dropdown filters orders correctly across channel + status views, AND-composes with status chips and search, and persists across tab switches. | Manual QA | Yet to test
POS2-002 Phase 3.1 | Validate platform counter chip shows live POS / Web counts and per-status sub-breakdown and increments correctly on new arrivals. | Manual QA | Yet to test
POS2-005 | Validate Status-8 orders are hidden from running dashboard and appear under Hold tab with HOLD label and no Collect Bill action. | Manual QA | Yet to test
POS2-005 | Validate Status-9 / paylater orders still behave as Hold and Collect Bill action remains available (status-8 vs status-9 differentiator). | Manual QA | Yet to test
POS2-005 | Validate prepaid orders show PAID badge / state correctly in reports and on cards. | Manual QA | Yet to test
POS2-006 | Validate single Payment Gateway dropdown (ALL / Non-PG / PG) is visible on all report tabs, defaults to ALL, and persists when switching tabs. | Manual QA | Yet to test
POS2-006 | Validate PG filter narrows results correctly (ALL = no filter, Non-PG = non-Razorpay, PG = Razorpay-only with PG columns surfaced). | Manual QA | Yet to test
POS2-007 Phase 1 | Validate default confirm-order tone (doorbell) plays when profile has no tone set. | Manual QA | Yet to test
POS2-007 Phase 1 | Validate confirm_order_tone = 'silent' results in no audio on YTC arrival (requires admin profile flip). | Manual QA | Yet to test
POS2-007 Phase 1 | Validate confirm_order_tone = 'buzzer' plays buzzer audio on YTC arrival (requires admin profile flip). | Manual QA | Yet to test
POS2-007 Phase 1 | Validate Sidebar Silent Mode kills all tones regardless of profile setting. | Manual QA | Yet to test
POS2-003 main | Validate Place Order wire carries correct printer_agent (KOT stations) on a tenant with non-empty print_agent configured. | Manual + Wire QA | Yet to test
POS2-003 FU-02 | Validate manual Print Bill from Order Entry header carries BILL agent on wire (tenant with non-empty print_agent). | Manual + Wire QA | Yet to test
POS2-003 FU-02 | Validate postpaid auto-print after Collect Bill carries BILL agent on wire (tenant with non-empty print_agent). | Manual + Wire QA | Yet to test
POS2-003 REOPEN-A | Validate Update / Edit Order wire carries printer_agent for affected KOT stations (tenant with non-empty print_agent). | Manual + Wire QA | Yet to test
POS2-003 REOPEN-A | Validate Cancel Item wire carries printer_agent for the impacted station (tenant with non-empty print_agent). | Manual + Wire QA | Yet to test
POS2-003 REOPEN-A | Validate Cancel Order wire carries printer_agent for impacted KOT stations and BILL is excluded (tenant with non-empty print_agent). | Manual + Wire QA | Yet to test
POS2-003 REOPEN-B | Validate Place Order v2 endpoint smoke — socket emit + FCM YTC tone + audit log all fire on one test order. | Manual QA | Yet to test
A-1 | Validate channel-based menu visibility — Order Entry shows only items eligible for the currently selected channel (dineIn / takeaway / delivery / web). | Manual QA | Yet to test
A-1 | Validate cart channel-switch prompt appears when operator changes channel mid-order (discard / keep cart). | Manual QA | Yet to test
SECTION C — Parked / Backend / Owner-decision items
CR-013 Bean Me Up | Validate Bean Me Up SC-GST print double-count once owner picks Option A/B/C/D and backend BE-G7/G8/G10/G11 ship. | Owner Decision | Yet to test
CR-013 Phase 3 | Validate delivery_charge_gst_amount appears as a separate persisted field on print payload (BE-G9). | Backend-blocked | Yet to test
CR-009 | Validate Operations Audit Timeline screen renders order operations from backend operations[] block once FE planning + implementation ships. | Ready to plan | Yet to test
CR-002 | Validate unified status & tab logic across reports once scope locks (owner prioritisation pending). | Owner Decision | Yet to test
CR-010 | Validate Roles & Permissions consolidation once owner prioritises and BE clarifies dependencies. | Owner Decision | Yet to test
CR-011 | Validate PG scan / Serve / paymentType case canonicalisation once backend ships (BE-A). | Backend-blocked | Yet to test
CR-012 | Validate Big Buddha filling MAX label mismatch fix once owner prioritises. | Owner Decision | Yet to test
UX-LOADING-02 | Validate faster login + visible station-load progress once owner picks A1/A2/A3 + B1/B2/B3 options. | Owner Decision | Yet to test
CR-008 #4 Phase B | Validate server-side persistence of Stay-on-Order-Entry preference once backend exposes default_landing_screen (BE-F). | Backend-blocked | Yet to test
CR-008 Sub-CR #3 | Validate Delivery dispatch / assign / picked-up flow once backend endpoint contract lands. | Backend-blocked | Yet to test
CR-005 B2 Phase 2 | Validate PG Status column auto-reveals once backend populates snapshot_razorpay_status (BE-W2). | Backend-blocked | Yet to test
POS2-003 PROFILE | Validate POS2-003 PROFILE endpoint v1→v2 flip — currently PARKED (owner: keep PROFILE as-is). | Owner Decision | Yet to test
POS2-008 Phase 2 | Validate backend-owned canonical tone token + FE override cleanup once backend ships Phase 2. | Backend-blocked | Yet to test
A-1 | Validate Product API field mapping for channel eligibility once backend confirms field map (manual device validation pending). | Backend-blocked | Yet to test
A-2 | Validate item is_disable + status kill-switch once backend confirms scope (not started). | Backend-blocked | Yet to test