## 📊 Summary
MyGenie POS 5 — Sprint Tracker
Generated 2026-08-05 ¦ Total: 271 items across POS 5.x sprints
Status | Count | Action Required
Owner Verified | 13 | No action needed
Closed | 8 | No action needed
Awaiting Smoke | 61 | 🟡 Schedule owner smoke session
QA Passed | 111 | 🟡 Queue for owner smoke session
Implemented | 10 | 🔵 Run QA testing
Plan Ready | 2 | 🟣 Owner: give Gate 4 GO
Impact Done | 2 | 🟠 Proceed to Gate 3 plan
Intake | 21 | ⬜ Assign to planning sprint
Blocked | 6 | 🔴 Escalate to backend team
Investigation | 3 | 🔍 Continue root-cause analysis
Deferred | 4 | ⏸ Review in next sprint
Closed (N/A) | 14 | Superseded / subsumed
Other | 16 | Review manually
TOTAL | 271

## 📋 All Items
ID | Type | Priority | Risk | Status | Gate | Sprint | Title | Notes
BUG-166 | BUG | P0 | MEDIUM | Owner Verified | 5 | pos_5_0 | addon_amount not multiplied by item qty in place-order and collect-bill payloads
BUG-250 | BUG | P0 | HIGH | Owner Verified | 0-5a | pos_5_0 | Polling Reconciliation Removes Aggregator Orders (~60s)
BUG-134 | BUG | P1 |  | Owner Verified |  | pos_5_0 | Scroll Not Working on Multiple Screens (Place Order, QSR) — Windows-Specific, Intermittent
BUG-137 | BUG | P1 | MEDIUM | Owner Verified |  | pos_5_0 | KOT Re-Print from Inside View (CartPanel) Fails — getOrderById Undefined | getOrderById not destructured from useOrders() in RePrintOnlyButton. Single line fix.
BUG-251 | BUG | P1 | LOW | Owner Verified | 0-5a | pos_5_0 | OrderCard Shows Cancel + WhatsApp for Aggregator Orders
BUG-253 | BUG | P1 | LOW | Owner Verified | 0-5a | pos_5_0 | Platform Dropdown Missing Aggregator Filter
BUG-254 | BUG | P1 | LOW | Owner Verified | 0-5a | pos_5_0 | Aggregator API Handlers Fail Silently (No Toast)
BUG-255 | BUG | P1 | LOW | Owner Verified | 0-5a | pos_5_0 | Item-Level Ready/Serve Dots Shown for Aggregator Orders
BUG-256 | BUG | P1 | LOW | Owner Verified | 0-5a | pos_5_0 | Revert BUG-252: TableCard Aggregator Body Makes Cards 2× Height
BUG-257 | BUG | P1 | LOW | Owner Verified | 0-5a | pos_5_0 | OrderCard item.qty Undefined for Aggregator — Empty Parens Display
CR-047 | CR | P1 |  | Owner Verified |  | pos_5_0 | AGENT_PROMPT_ALPHA v0.6 — Role Hardening (Intake, QA, Bug Fix, Investigation)
BUG-252 | BUG | P2 | MEDIUM | Owner Verified | 0-5a | pos_5_0 | TableCard Missing Items/Customer/Rider for Aggregator per Design
CR-106 | CR | ? | HIGH | Owner Verified | 0-6 ✅ | pos_5_0 | Aggregator Integration Module (UrbanPiper / Swiggy / Zomato) | ID collision resolved: original CR-105 intake doc on swiggy branch renumbered to CR-106. Distinct from CR-105 (Smart Purchase Show All). LARGE blast radius (~15 files). Touches R5 hotspots (OrderCard,…
BUG-142 | BUG | P0 | HIGH | Closed | 5a | pos_5_0 | POS Qty input — with NumLock ON qty becomes negative | R6 (order-value impact). Keypad Numpad-minus likely captured by qty step handler. Confidence: REPORTED.
BUG-125-B | BUG | P1 |  | Closed |  | pos_5_0 | Food Type (item_type) not persisting on Edit — imported from discount-menu branch
CR-010 | CR | P1 |  | Closed |  | pos_5_0 | Weight-based menu item support (item_unit / item_unit_price) | Registered 2026_06_01 via conversational intake
BUG-146 | BUG | P2 | LOW | Closed |  | pos_5_0 | Item-level scheduled time missing on OrderCard | Code verified: OrderCard.jsx lines 456-467 render SCH badge with formatted date/time from order.scheduleAt. Implemented as part of CR-018. Owner directed close 2026-07-09.
BUG-187 | BUG | P2 | LOW | Closed | 5a | pos_5_0 | Validation style inconsistency — red border missing on customer name in takeaway
CR-055 | CR | P2 | MEDIUM | Closed |  | pos_5_0 | OrderCard — served items visible by default (invert current collapse) | Code verified: OrderCard.jsx:54 useState(false), lines 698-730 served section with toggle. Served items are behind a collapsible toggle. Owner accepted current behavior.
BUG-093 | BUG | P3 |  | Closed |  | pos_5_0 | Room check-in date missing in API response | checkin_date fully mapped: orderTransform.js:406, roomOrdersService.js:44, RoomOrdersMockup.jsx, RoomRowCard.jsx, Excel/PDF exports. 3-level fallback chain. createdAt safety net retained.
BUG-101 | BUG | P3 |  | Closed |  | pos_5_0 | Print template GST display slot
BUG-138 | BUG | P0 | CRITICAL | Awaiting Smoke | 5b | pos_5_0 | Discount Payload — order_discount and self_discount Wrong Values | self_discount hardcoded 0 (should be manual+preset). order_discount uses discounts.total (includes coupon/loyalty/wallet — should be manual+preset only). 3 payment paths × 2 fields.
BUG-158 | BUG | P0 | LOW | Awaiting Smoke | 5b | pos_5_0 | CR-059 Setup — Add Item to category silently fails (PUT ignores stock_title)
BUG-159 | BUG | P0 | LOW | Awaiting Smoke | 5b | pos_5_0 | CR-059 Setup — Add Category silently fails (empty stock_title → HTML redirect misread as 200)
BUG-168 | BUG | P0 | CRITICAL | Awaiting Smoke | 5b | pos_5_0 | Bill print omits addons on dashboard/reports reprint (fallback subtotal loop misses add_ons[])
BUG-290 | BUG | P0 | LOW | Awaiting Smoke | 5b | pos_5_0 | Aggregator Manual Print fires to wrong restaurant — aggrId passed instead of orderId
BUG-VQTY | BUG | P0 | MEDIUM | Awaiting Smoke | 5b | pos_5_0 | Variation quantity not multiplied by item qty in order/bill payloads
CR-082 | CR | P0 | CRITICAL | Awaiting Smoke |  | pos_5_0 | Socket Room-Join — FE must emit join('rest_<rid>') after socket connect so room-scoped backend events reach the POS client
CR-097 | CR | P0 | CRITICAL | Awaiting Smoke |  | pos_5_0 | Auto-Settle — Throttle/Stagger Concurrent Settle Calls on Dashboard Load
BUG-096 | BUG | P1 |  | Awaiting Smoke | 5b | pos_5_0 | Realtime FE updates for menu + hold/unpaid | Food edit works (BUG-116). Reorder works. Category not needed. Delete-food: backend emits, FE ignores. Intake updated 2026-06-15.
BUG-130 | BUG | P1 |  | Awaiting Smoke | 5b | pos_5_0 | Channel Visibility: Restaurant Settings Channels Not Reflected in POS Dashboard
BUG-135 | BUG | P1 |  | Awaiting Smoke | 5b | pos_5_0 | Bulk Editor — Save errors: inactive status not persisting + error messages not surfacing backend description (3 sub-items)
BUG-144 | BUG | P1 | MEDIUM | Awaiting Smoke | 5b | pos_5_0 | Token Number not on order tickets / not passed to print | IMPLEMENTED. 5 edits across 4 files. useToken gate on display + dailyToken passthrough on all print. Compiled with 0 new warnings.
BUG-150 | BUG | P1 | MEDIUM | Awaiting Smoke | 5b | pos_5_0 | DnD item bounces back — categoryId null in expenses-list API + hidden placeholder
BUG-151 | BUG | P1 | HIGH | Awaiting Smoke | 5b | pos_5_0 | Edit transaction fails — editRow.expense key ≠ data.exp_name in editExpenseEntry service
BUG-152 | BUG | P1 | HIGH | Awaiting Smoke | 5b | pos_5_0 | Delete transaction fails — wrong endpoint (DELETE /edit-expense returns 405; correct: /delete-expense)
BUG-154 | BUG | P1 | MEDIUM | Awaiting Smoke | 5b | pos_5_0 | Add expense: qty/price conditional logic — if item has unitPrice show qty + read-only calc amount; else hide qty
BUG-155 | BUG | P1 | LOW | Awaiting Smoke | 5b | pos_5_0 | Add expense: show optional category dropdown after free-text item entry (not for master items)
BUG-160 | BUG | P1 | MEDIUM | Awaiting Smoke | 5b | pos_5_0 | CR-059 Setup — Rename Category broken (no rename endpoint on backend)
BUG-161 | BUG | P1 | LOW | Awaiting Smoke | 5b | pos_5_0 | CR-059 Setup — Bulk Save new items silently fails (PUT ignores stock_title)
BUG-167 | BUG | P1 | LOW | Awaiting Smoke | 5b | pos_5_0 | Menu socket (food_update channel) lost on non-dashboard routes — useSocketEvents only mounted in DashboardPage
BUG-194 | BUG | P1 | MEDIUM | Awaiting Smoke | 5b | pos_5_0 | Payments report in Insights — completely empty / no data
BUG-195 | BUG | P1 | MEDIUM | Awaiting Smoke | 5b | pos_5_0 | Takeaway Orders — Name mandatory toggle not working
BUG-280 | BUG | P1 | HIGH | Awaiting Smoke | 5b | pos_5_0 | Customer Details Not Sent to Settle API from Collect Bill | E1b: +cust_name/cust_mobile/cust_membership_id to collectBillExisting payload. No email. CollectBillPanelDrawer cust_name blank (known limitation). 2026-07-31.
BUG-281 | BUG | P1 | HIGH | Awaiting Smoke | 5b | pos_5_0 | custGST/custGSTName Not Forwarded to Auto-Bill Print (4 Missing Sites) | 6 sites fixed (E1a+E1b+E2+E3+E4+E5+E6). Investigation missed M_NEW-A(L1496)+M_NEW-B(L1891) — both included. 2026-07-31.
BUG-282 | BUG | P1 | LOW | Awaiting Smoke | 5b | pos_5_0 | Aggregator Popup: Addons + Variations Not Displayed
BUG-286 | BUG | P1 | LOW | Awaiting Smoke | 5b | pos_5_0 | Aggregator KOT/Bill Buttons Hidden on OrderCard (canPrintBill Permission Gate)
BUG-288 | BUG | P1 | MEDIUM | Awaiting Smoke | 5b | pos_5_0 | Menu Management: Station Dropdown Only Shows KDS (Other Stations Missing) | Root cause CONFIRMED via curl (2026-07-31). API returns printers key + area_name field. Transform had wrong keys. Fix: 1 file, 2 lines (menuManagementTransform.js). Gate 3 revised.
BUG-ROOM-PAIDROOM | BUG | P1 | MEDIUM | Awaiting Smoke | 5b | pos_5_0 | paid_room field always empty on bill collection for room orders
CR-046 | CR | P1 |  | Awaiting Smoke | 5b | pos_5_0 | Control Dashboard v2.0 — Interactive Workflow Controller (login, batch queue, gate approvals, smoke cards)
CR-048 | CR | P1 |  | Awaiting Smoke | 5b | pos_5_0 | Auto-Sync Registry → Dashboard JSON (eliminate manual sync gap)
CR-049 | CR | P1 |  | Awaiting Smoke | 5b | pos_5_0 | Insights Module: Migrate FE Aggregation to Backend Aggregation Endpoints
CR-059 | CR | P1 | HIGH | Awaiting Smoke | 5b | pos_5_0 | Expense Module — Migration from Old POS to New POS | Phase 1 implemented. BUG-CR059-A (transform key fix) + BUG-CR059-B (edit row combobox) + DnD (category drag-and-drop) delivered.
CR-061 | CR | P1 | LOW | Awaiting Smoke | 5b | pos_5_0 | Expense Report — FE Build with Client-Side Aggregation | V3 implemented 2026-07-09. 6 files (2 new + 4 modified). Webpack compiled 0 errors 0 new warnings. Backward compat verified (ExpenseEntryPanel.jsx safe). EXIT GATE 5/5 PASS. Awaiting QA.
CR-067 | CR | P1 | MEDIUM | Awaiting Smoke | 5b | pos_5_0 | Expense Bulk Editor — Full Parity Redesign with Menu Management Pattern
CR-118 | CR | P1 | MEDIUM | Awaiting Smoke | 5b | pos_5_0 | Aggregator KOT & Bill Manual Print | Pre-implemented by prior session. All 20 verification checks PASS. Registry updated at Gate 5a.
CR-122 | CR | P1 | MEDIUM | Awaiting Smoke | 5b | pos_5_0 | Inventory: Rename 'Smart Purchase' → 'Stock Update' + Move Vendor Preview to Top | Gate 2+3 complete. 4 files, 9 edits. All ODs resolved. Ready for Gate 4 GO.
BUG-092 | BUG | P2 |  | Awaiting Smoke | 5b | pos_5_0 | Phone format contract undefined for room check-in
BUG-136 | BUG | P2 |  | Awaiting Smoke | 5b | pos_5_0 | Sidebar scroll jumps to top on navigation (Sidebar re-mounts per page) | P2. Fix options: A) shared InsightsLayout wrapper (MEDIUM), B) scroll position restore via context (SMALL), C) scrollIntoView active item (SMALL).
BUG-147 | BUG | P2 | LOW | Awaiting Smoke | 5b | pos_5_0 | Duplicate-item error toast doesn't include item name | Message at AddCustomItemModal.jsx:274 lacks name interpolation. Check ProductForm too. Confidence: REPORTED (grep-verified).
BUG-153 | BUG | P2 | MEDIUM | Awaiting Smoke | 5b | pos_5_0 | Add expense UX — category required blocks free-text entry; no cross-category item suggestions
BUG-156 | BUG | P2 | LOW | Awaiting Smoke | 5b | pos_5_0 | Add expense: default payment method should be Cash Draw (not empty)
BUG-157 | BUG | P2 | LOW | Awaiting Smoke | 5b | pos_5_0 | Expense Setup DnD: category pills too small — need bigger padding for 6-8 category usability
BUG-175 | BUG | P2 | LOW | Awaiting Smoke | 5b | pos_5_0 | Expense Entry Form Case A: qty input shown when item has unit price — should be hidden
BUG-176 | BUG | P2 | LOW | Awaiting Smoke | 5b | pos_5_0 | Expense Entry Form Case B: optional qty/unit/physical_qty hidden; physical_quantity wrongly deprecated
BUG-188 | BUG | P2 | LOW | Awaiting Smoke | 5b | pos_5_0 | Order screen — Discount section alignment issue
BUG-283 | BUG | P2 | LOW | Awaiting Smoke | 5b | pos_5_0 | Aggregator: 'Order Instructions :::' Prefix Not Stripped from Zomato Notes
BUG-284 | BUG | P2 | LOW | Awaiting Smoke | 5b | pos_5_0 | Aggregator: Address Shows Duplicate City ('Bangalore, Bangalore')
BUG-285 | BUG | P2 | LOW | Awaiting Smoke | 5b | pos_5_0 | Aggregator OrderCard: 'Ready to Dispatch' Should Be Text Label, Not Button
BUG-287 | BUG | P2 | LOW | Awaiting Smoke | 5b | pos_5_0 | Aggregator: 'This is order level instructions' Default Placeholder Not Stripped
BUG-289 | BUG | P2 | LOW | Awaiting Smoke | 5b | pos_5_0 | Restaurant Settings: Default Order Status Dropdown Has Wrong Labels (5 options incorrect) | OD-1: Manager (not Manger). OD-2: hint → 'Order flow configuration'. Fast Lane eligible.
CR-041 | CR | P2 |  | Awaiting Smoke | 5b | pos_5_0 | Sidebar Restructure: Reorder, Rename, Panel→Route Migration, Settings Consolidation
CR-045 | CR | P2 |  | Awaiting Smoke | 5b | pos_5_0 | Insights Module: Suppress/Ignore Unused API Response Fields (FE Strip)
CR-051 | CR | P2 | MEDIUM | Awaiting Smoke | 5b | pos_5_0 | Customer Field Mandatoriness Override (Visibility Section) | 6 toggles: walkin name/phone, dinein name/phone, takeaway name (ON)/phone (OFF). 3 validation sites. TakeAway Name was hardcoded mandatory, now toggle-controlled with default ON.
CR-052 | CR | P2 | LOW | Awaiting Smoke | 5b | pos_5_0 | Sidebar Hover Flyout — collapsed sidebar shows popover with children on hover/click | Flyout popover for collapsed sidebar. 39 pages sidebar default changed true→false. BUG-139 superseded.
CR-066 | CR | P2 | MEDIUM | Awaiting Smoke | 5b | pos_5_0 | Unit Price Management: owner-only route for setting/editing expense stock item unit prices
CR-120 | CR | P2 | LOW | Awaiting Smoke | 5b | pos_5_0 | Aggregator: Split KOT/Bill Buttons by Order Status (Preparing→KOT, Ready→Bill)
CR-123 | CR | P2 | LOW | Awaiting Smoke | 5b | pos_5_0 | Stock Update: 'Update Stock' Button Sticky Fixed Bottom-Right
BUG-202 | BUG | ? | HIGH | Awaiting Smoke | 2 | pos_5_0 | Expense Setup — no Edit Item (rename + change category) capability; DnD workaround unsafe | Curl-verified 2026-07-17: PUT /expense/expenses/{id} with {stock_title, category_id} works (200 + echo). Unit_price FK survives PUT. Deviations from BACKEND_BRIEF_BUG202 spec: (a) payload key = stock_…
BUG-234 | BUG | ? | LOW | Awaiting Smoke | 0-5b | pos_5_0 | Employee Role Dropdown Shows System Roles + Silent ID Mismatch
BUG-235 | BUG | ? | MEDIUM | Awaiting Smoke | 0-5b | pos_5_0 | Role Permissions Save Fails with 422 — role_type Empty on Create/Toggle
CR-096 | CR | ? | LOW | Awaiting Smoke | 0-5b | pos_5_0 | Role Type Derivation from Template map_role (Option A)
BUG-185 | BUG | P0 | CRITICAL | QA Passed | 0-1 | pos_5_0 | Day Closure / Settlement — Opening balance logic not working correctly (INVESTIGATION) | BUG-185 fix applied 2026-07-14: replaced 9 instances of totalFunds-settled with balanceToSettle in SettlementPanel.jsx. Awaiting QA verification on preprod.
BUG-206 | BUG | P0 | HIGH | QA Passed |  | pos_5_0 | RecipeBulkEditor Batch Save fails — foodId null payload (BUG-197 #7 not ported to Bulk Editor)
BUG-164 | BUG | P1 | LOW | QA Passed | 0-2 | pos_5_0 | Add Category: duplicate name shows success toast instead of error
BUG-165 | BUG | P1 | LOW | QA Passed | 0-2 | pos_5_0 | Add Item: duplicate item name silently allowed — backend creates duplicate
BUG-179 | BUG | P1 | MEDIUM | QA Passed | 5b | pos_5_0 | Expense Report: Excel export produces empty file — wrong argument shape to exportReportAsExcel
BUG-180 | BUG | P1 | MEDIUM | QA Passed | 5b | pos_5_0 | Expense Report: PDF export throws error — wrong arguments to exportReportAsPDF (missing openReportWindow)
BUG-186 | BUG | P1 | HIGH | QA Passed | 5b | pos_5_0 | Day Closure / Settlement — Unable to settle payment in Partial mode | BUG-186 resolved as side-effect of BUG-185 fix. No additional code changes. Awaiting QA verification.
BUG-203 | BUG | P1 | MEDIUM | QA Passed | 0-2 | pos_5_0 | Unit price edit/add gaps across all expense contexts (4 sub-issues: A=Stock Master DONE, B=Bulk new row, C=Bulk edit silent fail, D=Edit expense qty/amount) | Scope expanded 2026-07-17: Sub-A (Stock Master inline edit) shipped. Sub-B (Bulk Editor new row cant set price), Sub-C (Bulk Editor edit price silently fails — missing pricedItems prop), Sub-D (Edit e…
BUG-204 | BUG | P1 | MEDIUM | QA Passed | 5a | pos_5_0 | Add Expense: priced items (Case A) hide qty input — amount locked to unitPrice×1, cannot enter quantity for multi-unit purchases | All 3 OQs locked by owner 2026-07-17. Ready for Gate 2 Planning.
BUG-207 | BUG | P1 | MEDIUM | QA Passed |  | pos_5_0 | RecipeBulkEditor Cost=₹0 Margin=100% — ingredient cost data not returned by recipe API
BUG-208 | BUG | P1 | MEDIUM | QA Passed |  | pos_5_0 | Expense Bulk Edit price reverts after save + Unit Price removal UX gaps
BUG-210 | BUG | P1 | MEDIUM | QA Passed |  | pos_5_0 | Dashboard Widget Data Calculation Errors — 4 fixes: Reorder Forecast negative-stock filter, Cost Trend 7d window too narrow, KPI ignores OOS items, rate missing units
BUG-240 | BUG | P1 | LOW | QA Passed | 5b | pos_5_0 | Smart Purchase: On-Hand Shows Small Unit (gm) Instead of Display Unit (kg) | Q1 APPROVED. calQuantity(gm) → displayQty(kg). ~5 lines, 1-2 files.
BUG-241 | BUG | P1 | LOW | QA Passed | 5b | pos_5_0 | Smart Purchase: Rate Auto-Fills From Vendor History Making Unselected Items Active | Q3 APPROVED. Don't auto-fill rate, show as suggested hint. ~8 lines, 2 files. CR-103 gap.
BUG-242 | BUG | P1 | LOW | QA Passed | 5b | pos_5_0 | Smart Purchase: No Default Vendor + Allows Submit With Null Vendor | Q4 APPROVED. Default System Vendor + block null vendor submit. ~10 lines, 1 file.
BUG-270 | BUG | P1 | LOW | QA Passed | 0-5 | pos_5_0 | Update Order Missing cust_mobile / cust_membership_id in update-place-order Payload
BUG-271 | BUG | P1 | CRITICAL | QA Passed | 0-5 | pos_5_0 | GST/VAT Wrong on Print from Dashboard/Order Page (Manual Print Path Uses Proportional Split)
BUG-274 | BUG | P1 | LOW | QA Passed | 0-5 | pos_5_0 | Bulk Delete in Ingredient Bulk Editor Not Working — handleSave Early Return Blocks Delete Processing
BUG-277 | BUG | P1 | LOW | QA Passed | 0-5 | pos_5_0 | Ingredient Bulk Editor: Multi-Select Checkbox Resets on 2nd Row Click
BUG-278 | BUG | P1 | LOW | QA Passed | 0-5 | pos_5_0 | Ingredient Bulk Editor: DELETE API Called Twice Per Ingredient (400 Bad Request)
CR-060 | CR | P1 | MEDIUM | QA Passed | 5 | pos_5_0 | Table/Room Management — Wire CRUD APIs to Existing UI | Gate 4 GO received. Implementation complete 2026-07-14. 6 files (5 modified + 1 new). Webpack 0 new warnings. Awaiting QA.
CR-069 | CR | P1 | CRITICAL | QA Passed | 5 | pos_5_0 | Employee Management + Role Management (Migration Wave 1)
CR-072 | CR | P1 | HIGH | QA Passed | 5 | pos_5_0 | Inventory Management — Migration from Old POS
CR-073 | CR | P1 |  | QA Passed | 3 | pos_5_0 | Recipe Bulk Editor — Inline Spreadsheet for Recipe Management (92+ recipes)
CR-077 | CR | P1 |  | QA Passed | 1 | pos_5_0_wave_2 | Hierarchy Stock Transfer — Receive · Dispatch · Dispute · Return (split from CR-075 P5 per B15)
CR-078 | CR | P1 |  | QA Passed | 1 | pos_5_0_wave_2 | Smart Purchase — Item-First Planner with Velocity & Vendor Intelligence (split from CR-075 per Q10-a)
CR-083 | CR | P1 | MEDIUM | QA Passed |  | pos_5_0 | Expense Split/Partial Payment — split single expense across multiple payment methods (Cash+UPI, Paid+Unpaid)
CR-084 | CR | P1 | MEDIUM | QA Passed |  | pos_5_0 | Vendor Management CRUD Screen — wire GET/PUT/DELETE vendor endpoints to VendorsTab. Replace vendor-types with actual vendor list.
CR-098 | CR | P1 | LOW | QA Passed | 0-3 | pos_5_0 | Short Code (Item Code) Display on Order Card
CR-099 | CR | P1 | MEDIUM | QA Passed | 0-3 | pos_5_0 | Per-Item Preparation & Serve Time Display on Order Card
CR-102 | CR | P1 | LOW | QA Passed | 0-3 | pos_5_0 | Inventory Add/Edit: Send consumption_unit in Payload (G-020 Alignment) | FE sends small_unit + converion_factor but backend G-020 requires consumption_unit + converion_factor. Fix: repurpose smallUnit → consumption_unit in toAPI. ~4 lines, 1 file. Related: BUG-226.
CR-103 | CR | P1 | MEDIUM | QA Passed | 0-3 | pos_5_0 | Smart Purchase: Bulk Remove UX (Select All + Prominent Cross Button) | 3 sub-items: (A) validate blocks without all rows filled, (B) × button too small/subtle, (C) no select-all/bulk-remove. ~30-50 lines, 2 files. Not Fast Lane (2 files + state change).
CR-116 | CR | P1 | MEDIUM | QA Passed | 0-5 | pos_5_0 | B2B Customer GST & Name Capture — New Input Fields in Collect Bill
BUG-162 | BUG | P2 | MEDIUM | QA Passed | 5a | pos_5_0 | CR-059 Setup — Expense Setup panel flickers on every mutation (fetchAll full re-fetch pattern) | Owner ruling 2026-07-16: Setup panel flicker (fetchAll full re-fetch) will be fixed as part of CR-074-B redesign via optimistic local updates.
BUG-177 | BUG | P2 | LOW | QA Passed | 5b | pos_5_0 | Expense Entry: notes field missing from add form — backend accepts notes but FE form + payload omit it
BUG-178 | BUG | P2 | LOW | QA Passed | 5b | pos_5_0 | Expense Entry: item name editable via ItemCombobox in transaction edit — should be read-only
BUG-181 | BUG | P2 | LOW | QA Passed | 5b | pos_5_0 | Expense Entry: Added By column missing from daily transaction table — data available but not rendered
BUG-205 | BUG | P2 | LOW | QA Passed |  | pos_5_0 | Expense: Qty/Unit columns missing from transaction table + report
BUG-237 | BUG | P2 | LOW | QA Passed | 0-5 | pos_5_0 | Recipe Form — Recipe Name Field Should Be Hidden for Standard & Addon Types (Auto-Derived from Item Selection) | Standard recipe: name field dead UI (transform sends foodId). Addon: should auto-derive from addon item name. Sub-recipe: user-typed (correct). 1 file, ~15 lines. Fast Lane eligible.
BUG-238 | BUG | P2 | LOW | QA Passed | 0-5 | pos_5_0 | Recipe Form — Replace Plain <select> Dropdowns with Searchable Combobox | Menu Item (280 foods), Addon Item, Ingredient (246 items) — all replaced with SearchableSelect. QA 6/6 PASS.
BUG-239 | BUG | P2 | LOW | QA Passed | 0-5 | pos_5_0 | Recipe Form — Hide Serves Field for Sub-Recipe & Addon (Default 1) | Serves meaningless for sub/addon. Hide + default 1. 1 file, ~3 lines. Owner approved.
BUG-272 | BUG | P2 | LOW | QA Passed | 0-5 | pos_5_0 | Partial Payment Breakdown Missing in Order Report (partial_payments Not Parsed)
BUG-275 | BUG | P2 | LOW | QA Passed | 0-5 | pos_5_0 | Edit Ingredient: Conversion Factor Pre-Fills to 1 When No Conversion Exists
BUG-276 | BUG | P2 | LOW | QA Passed | 0-5 | pos_5_0 | Bulk Editor UX: Category Move Causes Item Jump + Inconsistent Delete Between Expense/Ingredient Editors
BUG-279 | BUG | P2 | LOW | QA Passed | 0-5 | pos_5_0 | Ingredient Bulk Editor: Header Not Sticky on Scroll
CR-056 | CR | P2 | MEDIUM | QA Passed | 0-2 | pos_5_0 | Restaurant Setting — toggle to show/suppress incoming scan-order popup | Default ON to preserve current behavior. Storage strategy (backend vs localStorage) owner ruling required. Confidence: REPORTED.
CR-062 | CR | P2 | MEDIUM | QA Passed | 0-2 | pos_5_0 | Expense Report — Backend Aggregation Contract | BLOCKED by CR-061. After CR-061 ships, create backend aggregation contract doc. Same pattern as CR-049.
CR-064 | CR | P2 | LOW | QA Passed | 1 | pos_5_0 | Add Item: include unit price field in quick-add form | Owner ruling 2026-07-16: unit-price field on quick-add form folded into CR-074-B redesign scope so both ship together.
CR-079 | CR | P2 |  | QA Passed | 1 | pos_5_0_wave_2 | Inventory Information Architecture Restructure — Intelligence-as-Dashboard (split from CR-075 per FB-5)
CR-101 | CR | P2 | LOW | QA Passed | 0-3 | pos_5_0 | Daily Report — Collected By + Punched By Filter Dropdowns on Settled Tab | Data exists (punchedBy, actionedBy in reportTransform). FilterBar has no employee dropdown. Client-side filter from unique values. ~20-30 lines, 2-3 files.
CR-107 | CR | P2 | HIGH | QA Passed | 0-2 | pos_5_0 | Aggregator Auto-Accept (with Dynamic Prep Time)
CR-109 | CR | P2 | LOW | QA Passed | 0-5a | pos_5_0 | Dynamic Prep Time + Auto-Accept for Aggregator (no KOT/bill — separate CR)
CR-110 | CR | P2 | LOW | QA Passed | 0-5a | pos_5_0 | MyGenie Brand Badge for Own Delivery Orders
CR-111 | CR | P3 | LOW | QA Passed | 0-5a | pos_5_0 | OrderCard Aggregator Item Format: ● Qty× Name Pattern
CR-112 | CR | P3 | LOW | QA Passed | 0-5a | pos_5_0 | OrderCard Item Price Display (₹ per item line)
CR-113 | CR | P3 | LOW | QA Passed | 0-5a | pos_5_0 | OrderCard Customer+Phone Section for Aggregator
BUG-196 | BUG | ? | LOW | QA Passed | 5 | pos_5_0 | Sidebar missing on 6 inventory/employee pages
BUG-197 | BUG | ? | HIGH | QA Passed | 5 | pos_5_0 | CR-072 Inventory Post-Delivery — 10 gaps (recipe CRUD, purchase Amount, vendor save, wastage CRUD, add ingredient, form validation)
BUG-198 | BUG | ? | HIGH | QA Passed | 1 | pos_5_0 | CR-069 Employee Post-Delivery — 4 issues (update POST→PUT, add missing fields, reset password 3-bug stack, eye icon missing)
BUG-199 | BUG | ? | MEDIUM | QA Passed | 5 | pos_5_0 | Expense Entry — new item always goes to misc category (categoryId not serialized to API payload)
BUG-201 | BUG | ? | HIGH | QA Passed |  | pos_5_0 | Expense Deletion Safety — item + category cascade delete warning
BUG-211 | BUG | ? | MEDIUM | QA Passed |  | pos_5_0 | Current Stock — No default sort (low stock buried) + KPI cards not clickable as filters
BUG-212 | BUG | ? | HIGH | QA Passed |  | pos_5_0 | Ingredients — Edit missing (backend exists, FE unwired) + Add form incomplete (missing 4 fields) + Export button fake (toast only)
BUG-213 | BUG | ? | LOW | QA Passed |  | pos_5_0 | IngredientBulkEditor — Bulk Edit toolbar has no page title (G8 gap from CR-086 F4)
BUG-214 | BUG | ? | HIGH | QA Passed | 0-5b ✅ | pos_5_0 | Addon Recipe Dropdown Shows Menu Items Instead of Addon Items
BUG-215 | BUG | ? | MEDIUM | QA Passed | 0-5b ✅ | pos_5_0 | Recipe Forms — Validation Errors Not Shown on Save Failure
BUG-216 | BUG | ? | HIGH | QA Passed | 0-5b ✅ | pos_5_0 | Recipe Ingredient Row Shows Base Unit, Should Show Small Unit
BUG-217 | BUG | ? | MEDIUM | QA Passed | 0-5b ✅ | pos_5_0 | Sub-Recipe Serves Field Not Required But Blocks Save
BUG-218 | BUG | ? | HIGH | QA Passed | 0-5b ✅ | pos_5_0 | Delete Ingredient — No Blocking Error When Used in Recipe
BUG-219 | BUG | ? | HIGH | QA Passed | 0-5b ✅ | pos_5_0 | Ingredient Form — Min Unit Text Input, Factor/Min Q/Min U Labels Unclear
BUG-220 | BUG | ? | LOW | QA Passed | 0-5b ✅ | pos_5_0 | Ingredient Category — No Duplicate Alert, No Edit/Delete
BUG-221 | BUG | ? | HIGH | QA Passed | 0-5 ✅ (FE) | pos_5_0 | Bulk Ingredient Upload & Excel Download Not Working
BUG-222 | BUG | ? | HIGH | QA Passed | 0-5 ✅ (FE) | pos_5_0 | Bulk Recipe Excel — No Template/Export Split; File Won't Open
BUG-223 | BUG | ? | HIGH | QA Passed | 0-5b ✅ | pos_5_0 | Wastage & Recipe Deduction Auto-Trigger Without Explicit Save
BUG-224 | BUG | ? | HIGH | QA Passed | 0-5b ✅ | pos_5_0 | Smart Purchase — Ingredients Without Recipes Never Appear
BUG-226 | BUG | ? | HIGH | QA Passed | 0-5b ✅ | pos_5_0 | Conversion Factor Not Saved on Add or Edit Ingredient
BUG-227 | BUG | ? | HIGH | QA Passed | 0-5b ✅ | pos_5_0 | Smart Purchase — Vendor Column Shows No History Though Vendors Exist
BUG-229 | CR | ? | LOW | QA Passed | 0-5 ✅ | pos_5_0 | Employee: Auto-Populate Email (User ID) as firstname@restaurantname.com | Auto-generate email as firstname@restaurantname.com on new employee. Email MANDATORY (reverses BUG-198). Code reality: NONE. Blast radius: SMALL (1 file, ~20 lines).
BUG-230 | CR | ? | LOW | QA Passed | 0-5 ✅ | pos_5_0 | Employee: Name Change → Email Auto-Sync (if auto-generated) | If name changes and email was auto-generated → re-generate. If manually edited → do NOT overwrite. Code reality: NONE. Depends on BUG-229. Blast radius: SMALL (1 file, ~10-15 lines).
BUG-231 | BUG | ? | LOW | QA Passed | 0-5 ✅ | pos_5_0 | Role Form: Hide role_type Field + Add Save Error Toasts | Sub-A: Hide role_type dropdown (backend maps via template). Sub-B: Error toasts — code already has toast.error at L111, verify if sufficient. Code reality: PARTIAL (role_type UI exists, needs removal;…
BUG-232 | BUG | ? | LOW | QA Passed | 0-5b ✅ | pos_5_0 | By Ingredient tab — empty combobox / no data on fast navigation (loading race)
BUG-244 | BUG | ? | MEDIUM | QA Passed | 5b | pos_5_0 | add-purchase payload: wrong payment key + missing header totals
BUG-245 | BUG | ? | LOW | QA Passed | 5b | pos_5_0 | Table card moves to top when order placed (occupied-first bucketing)
BUG-246 | BUG | ? | MEDIUM | QA Passed | 5b | pos_5_0 | Customized items not merging in cart (duplicate line items + print)
BUG-247 | BUG | ? | LOW | QA Passed | 5b | pos_5_0 | Smart Purchase ad-hoc typeahead blocks UI (perf — no React.memo)
BUG-248 | BUG | ? | LOW | QA Passed | 5b | pos_5_0 | Bulk Editor: 9 columns missing from isDirty — edits silently lost (Save never triggers)
BUG-249 | BUG | ? | LOW | QA Passed | 5b | pos_5_0 | Current Stock: Negative quantity items show "In Stock" badge — field mismatch (quantity vs displayQty)
BUG-258 | BUG | ? | MEDIUM | QA Passed |  | pos_5_0 | P&L Report Calendar Broken / Different UI — No Presets, No Max Date | PLReportPage uses raw <input type=date> without max, presets, or calendar component. Needs rewrite to match ExpenseReport pattern.
BUG-259 | BUG | ? | LOW | QA Passed |  | pos_5_0 | P&L Report Charts Hidden When ≤1 Data Point | chartData.length > 1 condition on line 182 too strict. Should be >= 1.
BUG-260 | BUG | ? | LOW | QA Passed |  | pos_5_0 | Future Dates Allowed in 5 Report Calendars | 5 reports missing max= on date inputs: PLReport, Consumption, EdgeStates, ItemSalesHybrid, Dashboard.
BUG-261 | BUG | ? | MEDIUM | QA Passed |  | pos_5_0 | Missing Preset Pills in P&L + Consumption Reports | P&L and Consumption lack [Today, 7D, 30D, MTD] preset pills. Owner confirmed standard pattern.
BUG-262 | BUG | ? | MEDIUM | QA Passed |  | pos_5_0 | Coming Soon Placeholders Visible in Production (6 Locations) | P0. Coming Soon visible in InventoryIntelligence (wastage), InventorySetup (import), Sidebar, LoginPage.
BUG-263 | BUG | ? | LOW | QA Passed |  | pos_5_0 | Smart Purchase — No Sticky Toolbar | Toolbar not sticky. CSS-only fix. Planning skip eligible.
BUG-264 | BUG | ? | LOW | QA Passed |  | pos_5_0 | System Vendor — No Explanation/Tooltip | System Vendor label confusing. No tooltip or explanation.
BUG-265 | BUG | ? | LOW | QA Passed |  | pos_5_0 | Conversion Factor — No Help Text | No tooltip or help text explaining conversion factor concept.
BUG-269 | BUG | ? | MEDIUM | QA Passed |  | pos_5_0 | Ingredient Add/Edit — 3 UX Bugs: Conversion Sent Incorrectly + No Small Unit Auto-Select + Alert Unit Not Read-Only | All 9 edits from plan applied. 2 files: inventoryTransform.js (hasConversion guard), InventorySetupPanel.jsx (auto-select + alert read-only + startEdit sync). Code markers: BUG-269-A/B/C.
CR-074 | CR | ? | MEDIUM | QA Passed | 5a | pos_5_0 | Expense Setup — remove Import/Export + design consistency refresh (match Menu Management) | -A: IMPLEMENTED 2026-07-16 (import/export removed + dead-code sweep). -B: IMPLEMENTED 2026-07-17 — 5 code phases shipped: P1 BUG-162 flicker fix (optimistic updates), P2 CR-064 unit-price quick-add + …
CR-085 | CR | ? | HIGH | QA Passed |  | pos_5_0 | Inventory Module Completion (Phase 2 Consolidation) — Design gaps, recipe backend blockers, unstarted features (Dispatch/S3/Column Toggle), code quality, registry sync
CR-086 | CR | ? | HIGH | QA Passed |  | pos_5_0 | Current Stock & Ingredients UX Overhaul — Card-based filters, proper export fields, PDF export, Ingredient Bulk Editor, Import wiring
CR-087 | CR | ? | MEDIUM | QA Passed |  | pos_5_0 | New Expense Payment Fields — payment_made_to + payment_ref_id
CR-088 | CR | ? | LOW | QA Passed | 0-5b ✅ | pos_5_0 | Recipe By Ingredient Reverse View Tab | Recipe By Ingredient reverse view tab. Additive — new tab + ingredient selector. Plan: /app/memory/plans/CR-088_IMPLEMENTATION_PLAN.md. Execution: after CR-092.
CR-089 | CR | ? | LOW | QA Passed | 0-3 | pos_5_0 | PDF Export for Standard Sub and Addon Recipes | PDF Export for Recipes. jsPDF client-side. Plan: /app/memory/plans/CR-089_IMPLEMENTATION_PLAN.md. Execution: after CR-092 + CR-088.
CR-090 | CR | ? | MEDIUM | QA Passed | 5b | pos_5_0 | Inventory Categories — Edit and Delete
CR-092 | CR | ? | LOW | QA Passed | 0-5b ✅ | pos_5_0 | Recipe Tabs — Sort Controls | Recipe Tabs Sort Controls. Client-side sort. Plan: /app/memory/plans/CR-092_IMPLEMENTATION_PLAN.md. Execution: FIRST in CR-088/089/092 cluster.
CR-093 | CR | ? | LOW | QA Passed | 0-5b ✅ | pos_5_0 | Consumption Report — New Screen (Date Range Category Ingredient Margin Cost)
CR-094 | CR | ? | MEDIUM | QA Passed | 0-5b ✅ | pos_5_0 | P&L Report — New Screen Under Daily Reports Above Sales | P&L Report (Daily Reports, Above Sales). New screen. Impact: /app/memory/impact/CR-094_IMPACT_ANALYSIS.md. Plan: /app/memory/plans/CR-094_IMPLEMENTATION_PLAN.md. Mock: /app/memory/evidence/CR-094/pl_r…
CR-095 | CR | ? |  | QA Passed | 0-5b ✅ | pos_5_0 | Waiter-to-Waiter Transfer — Unlock Settlement Feature | Unblock backend-blocked waiter transfer in settlement. Related: CR-015. Intake: /app/memory/change_requests/CR-095_WAITER_TRANSFER_UNLOCK_INTAKE.md. Impact: /app/memory/impact/CR-095_IMPACT_ANALYSIS.m…
CR-105 | CR | ? | LOW | QA Passed | 5b | pos_5_0 | Smart Purchase: Show All Ingredients + Manual Add to Purchase List
CR-114 | CR | ? | MEDIUM | QA Passed |  | pos_5_0 | Smart Purchase — Default All Items Unselected (Opt-In) | All items shown by default. Owner wants opt-in: items start unselected, user picks what to buy.
CR-115 | CR | ? | MEDIUM | QA Passed |  | pos_5_0 | Smart Purchase — Search Filter + Sort by Category | No search/filter/category sort in Smart Purchase. 100+ items unmanageable.
CR-125 | CR | ? | HIGH | QA Passed |  | pos_5_x | Aggregator Brand Name — Display on OrderCard + Include in Print Payload | brand_name from get-order-list top-level field. DISTINCT from CR-110 (own delivery badge). RELATED to CR-118 (aggregator print). OQ-3 blocking for print scope. Intake doc: change_requests/CR-125_AGGRE…
BUG-291 | BUG | P1 | LOW (revised from HIGH — socketHandlers.js NOT touched; GAP-R5 false alarm) | Implemented | 5a complete, QA next | pos_5_0 | Aggregator Rider Details Not Displayed (riderName/riderStatus/deliveryManId mapping gaps) | BUG-250 was already taken. New ID BUG-291 assigned. 3 real changes in aggregatorTransform.js only: (1) add rider: field, (2) add riderStatus derivation, (3) drop riderInfo block. GAP-R3 dropped (foote…
BUG-294 | BUG | P1 | HIGH | Implemented | 5 | pos_5_1 | CustomerModal — CRM Calls Block Order Flow on 401 (Non-Blocking Pattern Missing) | INTAKE ONLY. CustomerModal.jsx: 3 unprotected CRM calls (L285 updateCustomer, L307 lookupCustomer, L352 createCustomer) throw to outer catch on 401 → 'Failed to save customer' → order flow blocked. Fi…
BUG-295 | BUG | P1 | MEDIUM | Implemented | 5 | pos_5_1 | Room Check-In Docs Not Shown on Return Visit (INV-003: two root causes) | INV-003. RC2 (CODE_ERROR): setCrmCustomerId never called in handleSubmit — added at BUG-092 block. RC1 (PLAN_GAP): docs uploaded to POS only — added uploadDocument call after roomService.checkIn(). 4 …
CR-119 | CR | P1 | MEDIUM | Implemented | 5a complete — QA next | pos_5_0 | Aggregator Food Mapping — POS Menu to Platform Item Mapping | UNBLOCKED (2026-08-01). MD spec received. APIs probed: 74 agg foods, 100 recipes, 71 mapped on kunafamahal. Tab goes under RecipeManagementPanel. Impact Analysis in progress.
CR-124 | CR | P1 | MEDIUM-HIGH | Implemented | 5a complete — QA next | pos_5_0 | Call PaaS Logout API on User Logout (token invalidation + FCM deregistration) | authService.logout() is local-only — no backend call. 2 gaps: GAP-C1 token not invalidated server-side; GAP-C2 FCM device token not deregistered. Fix: fire-and-forget api.post(LOGOUT) + add LOGOUT to …
CR-127 | CR | P1 | LOW | Implemented |  | pos_5_1 | Room Check-In: Add cust_membership_id to Check-In Payload | Code complete. 1 edit (roomService.js). Compile PASS. EXIT GATE 4/5 PASS.
CR-128 | CR | P1 | HIGH | Implemented |  | pos_5_1 | B2B Customer CRM Wiring — Read + Write + Auto-Populate from CRM v2 Contract | Code complete. 8 edits, 2 files. CRM validated (G1a/G1b/G2b all PASS). Compile PASS. EXIT GATE 4/5 PASS.
BUG-292 | BUG | P2 | LOW | Implemented |  | pos_5_0 | Aggregator TableCard: AggrId truncated — amount pill competes for header space | Hide table.amount for isAggregator on TableCard header pill. 1 file, 2 lines. Fast Lane eligible.
BUG-293 | BUG | P2 | LOW | Implemented |  | pos_5_0 | OrderCard: Served items section collapsed by default — auto-expand when no active items remain | Lazy useState initializer + useEffect for real-time. 1 file, 2 edits. Fast Lane.
CR-129 | CR | P2 | HIGH | Implemented | 5 | pos_5_1 | Room Check-In — Document Preview & Selection from CRM (View existing + Upload to CRM) | INTAKE ONLY. FEATURE_GAP — intentionally deferred per owner Q7=B. CRM GET/POST /pos/customers/{id}/documents endpoints live. customerTransform parses documents (CR-128). Zero UI exists: no documentSer…
BUG-123 | BUG | P1 |  | Plan Ready |  | pos_5_0 | Place Order on 401 silently redirects to dashboard; cashier mistakes failure for success
BUG-273 | BUG | P2 | MEDIUM | Plan Ready | 0-3 | pos_5_0 | Auto Settle Local Settings Removal — Now Server-Side
BUG-225 | BUG | ? | LOW | Impact Done |  | pos_5_0 | Same Name Appears as Ingredient + Recipe; Unit Mismatch Across Screens
BUG-266 | BUG | ? | N/A | Impact Done |  | pos_5_0 | Wastage Report / Top Wasted Items — BACKEND-BLOCKED | Backend wastage report endpoints do not exist. Frontend placeholder ready. BACKEND_BRIEF needed.
BUG-118 | BUG | P1 |  | Intake |  | pos_5_0 | Nth-item coupon / BOGO coupon not working
BUG-183 | BUG | P1 | MEDIUM | Intake | 0-1 | pos_5_0 | Daily Report — Phone number and customer name missing in Credit tab
BUG-184 | BUG | P1 | MEDIUM | Intake | 0-1 | pos_5_0 | Daily Report — CRE-Credit payment type not reflecting in Payment column
BUG-189 | BUG | P1 | HIGH | Intake | 0-1 | pos_5_0 | Delivery — Accept Order option missing for rider login (INVESTIGATION)
BUG-190 | BUG | P1 | MEDIUM | Intake | 0-1 | pos_5_0 | Customer Notes not syncing with CRM / historical notes not showing (INVESTIGATION)
BUG-192 | BUG | P1 | MEDIUM | Intake | 0-1 | pos_5_0 | Prep & Serve Time — Handover time showing 0 + full logic investigation
BUG-193 | BUG | P1 | MEDIUM | Intake | 0-1 | pos_5_0 | Room Transfer Trail — showing table transfers + FROM ROOM showing 0 (INVESTIGATION)
CR-012 | CR | P1 |  | Intake |  | pos_5_0 | Menu Management — migrate to new API contract (scope-limited) | Registered 2026_06_01 via conversational intake
CR-057 | CR | P1 | CRITICAL | Intake |  | pos_5_0 | Menu Management — add "No Tax" option + document tax rules | R6 CRITICAL. Two-part: (A) document tax model, (B) add No-Tax option. Multiple owner rulings required. Full E2E money regression required. Confidence: REPORTED.
CR-058 | CR | P1 | HIGH | Intake |  | pos_5_0 | Order-level "Mark Order Complimentary" action + mandatory discount note | R6 CRITICAL. Order-level comp: flip all items + mandatory note. SUBSUMES BUG-145 (owner ruling 2026-07-04). 8 owner rulings required at Planning. Full E2E money regression required.
CR-068 | CR | P1 | HIGH | Intake | 0-1 | pos_5_0 | Cancellation role-gating — make cancellation rights role-based
CR-126 | CR | P1 | MEDIUM | Intake |  | pos_5_1 | Backdated Billing Date — User-selectable billing date on order punch (backend-config gated) | INTAKE ONLY. User can set billing date (incl. backdate) during order punch. Backend configuration controls feature availability. No implementation yet.
BUG-124 | BUG | P2 |  | Intake |  | pos_5_0 | Backend food_update socket payload missing critical fields (status, is_disable, stock_out, food_status, live_web)
BUG-191 | BUG | P2 | LOW | Intake | 0-1 | pos_5_0 | Customer Intelligence — Phone number missing in Insights section
BUG-209 | BUG | P2 | MEDIUM | Intake |  | pos_5_0 | Weight item qty display — Bill Summary missing unit labels (x100 instead of 100gm) + Receipt shows decimal Kg instead of gm
CR-043 | CR | P2 |  | Intake |  | pos_5_0 | Credit Per-Customer Totals in Reports + Portfolio Export Optimization
CR-121 | CR | P2 | MEDIUM | Intake | 0-1 | pos_5_0 | Dashboard Quick-Start: Single-Click Order for Delivery / Takeaway / Walk-in
BUG-040 | BUG | P3 |  | Intake |  | pos_5_0 | Audit Report Excel / CSV Export Format Must Follow Provided Format
BUG-041 | BUG | P3 |  | Intake |  | pos_5_0 | Audit Report PDF Download — Mixed / Misaligned Rows, Logic Review & Refinement Needed
CR-050 | CR | P3 |  | Intake |  | pos_5_0 | Insights Dashboard: Quarterly Comparison View (Q1 vs Q2 revenue card)
POS2-001 | CR | ? |  | Intake |  | pos_5_0 | Delivery charge / GST / web delivery lock | Possibly absorbed by shipped CRs
BUG-243 | BUG | P0 | CRITICAL | Blocked | 0-1 | pos_5_0 | Backend: Stock Not Credited After add-purchase (BACKEND-BLOCKED) | BACKEND-BLOCKED. Purchase recorded but quantity/cal_quantity/display_qty never updated. Brief filed. No FE workaround.
CR-100 | CR | P1 | HIGH | Blocked | 0-1 | pos_5_0 | Smart Purchase — Partial Payment, Reference ID, Notes & Unpaid Status | Backend contract change needed: partial_payments array, payment_ref_id, notes per vendor PO, payment_status (paid/unpaid/partial). FE ready to implement once backend delivers. Mirrors Expense CR-083 s…
BUG-090 | BUG | P2 |  | Blocked |  | pos_5_0 | CRM customer_id not stored on room orders
BUG-233 | BUG | ? | MEDIUM | Blocked |  | pos_5_0 | By Ingredient tab: addon recipes never show — addon-recipe-list returns ingredients:[] | Data loss risk: editing addon recipe overwrites ingredients with empty array
CR-091 | CR | ? | LOW | Blocked | 0-1 | pos_5_0 | Purchase — Transaction ID for Bank Transfer
CR-104 | CR | ? | MEDIUM | Blocked | 0-1 | pos_5_0 | Item-level complementary reason (mandatory note per food item)
BUG-236 | BUG | P1 | LOW | Investigation |  | pos_5_0 | Smart Purchase — Ad-hoc Typeahead Dropdown Clipped by overflow-hidden | overflow-hidden on card container clips absolute dropdown. 3 edits, ≤5 lines, 1 file.
BUG-267 | BUG | ? | LOW | Investigation |  | pos_5_0 | Inventory Setup — Category Not Selecting When Adding Ingredient | Cannot reproduce. Dropdown has 72 options, selection works in automation. Need owner repro steps/video.
BUG-268 | BUG | ? | CRITICAL | Investigation |  | pos_5_0 | Inventory Setup — Edit Ingredient Fails: inventory_audit_logs.id Missing AUTO_INCREMENT | BACKEND-BLOCKED. ALL ingredient edits fail with 500. Fix: ALTER TABLE inventory_audit_logs MODIFY id AUTO_INCREMENT.
CR-071 | CR | P1 | CRITICAL | Deferred | 0 | pos_5_0_wave_2 | App-Wide Role Gating / Permission Consumer Wiring (Migration Phase 3 — DEFERRED)
CR-108 | CR | P2 | MEDIUM | Deferred | 0-2 | pos_5_0 | Auto-KOT + Auto-Bill on Aggregator Accept — PARKED pending payload confirmation
BUG-228 | BUG | ? | MEDIUM | Deferred | 0-2 ✅ (DEFERRED) | pos_5_0 | Expense Split Bill: Item Appears as 2 Rows in Transaction List | Split bill (CR-083) causes duplicate row display. Code reality: PARTIAL (split save exists, display grouping does NOT). Blast radius: SMALL (1 file, ~20-30 lines).
CR-076 | CR | ? | MEDIUM | Deferred | 1 | pos_5_0 | Amazon S3 File Upload — Invoice attachments (Purchase/Receive) + Room Check-in document uploads
BUG-104 | BUG | P1 |  | Closed (N/A) |  | pos_5_0 | Credit/Tab Management module
BUG-105 | BUG | P1 |  | Closed (N/A) |  | pos_5_0 | Settlement Module | Settlement Module fully implemented via CR-015 (dashboard panel) + CR-016 (Insights report). Both CLOSED — OWNER VERIFIED.
BUG-129 | BUG | P1 |  | Closed (N/A) |  | pos_5_0 | Backend stamps TAB (credit) orders f_order_status=6 before money is collected | All 319 palmhouse + 141 cafe103 TAB orders have fStatus=6 at punch. Root cause of CR-030/TAB policy ambiguity: frontend cannot distinguish settled vs outstanding credit from the list payload. Backend …
BUG-140 | BUG | P1 | MEDIUM | Closed (N/A) |  | pos_5_0 | Bulk Editor — changing "Type" field doesn't save | Owner reports Bulk Editor Type field save issue cannot be reproduced. Closed per owner direction.
BUG-141 | BUG | P1 | MEDIUM | Closed (N/A) |  | pos_5_0 | Excel Import — "Type" column not captured on menu update | Owner reports Excel Import Type column issue cannot be reproduced. Closed per owner direction.
BUG-143 | BUG | P1 | MEDIUM | Closed (N/A) | 5a | pos_5_0 | Short Code toggle ON but not printing / not effective | Toggle wired end-to-end but consumer (bill/KOT template) not located. Confidence: REPORTED.
BUG-145 | BUG | P1 | HIGH | Closed (N/A) |  | pos_5_0 | Discount Type dropdown — "Complimentary" option missing | R6. RELATED to BUG-018/021 (SUBSUMED) but different surface (dropdown vs collect-bill flow). Owner ruling required on scope. Confidence: REPORTED. SUBSUMED by CR-058 (owner ruling 2026-07-04): order-l…
BUG-148 | BUG | P1 | MEDIUM | Closed (N/A) |  | pos_5_0 | Table Management — cannot add new table | Investigation 2026-07-17: 4 curl steps on cafe103 preprod. Full CRUD works. May have been temporary or restaurant-specific. Report: evidence/BUG148_BUG200_INVESTIGATION_REPORT_2026_07_17.md
BUG-149 | BUG | P1 | MEDIUM | Closed (N/A) |  | pos_5_0 | Order ID not visible on Scan & Delivery order cards | Owner reports issue cannot be reproduced. Code shows orderNumber chip renders for non-Room non-DineIn orders (OrderCard.jsx:426-432). Closed per owner direction.
BUG-182 | BUG | P1 | MEDIUM | Closed (N/A) | 1 | pos_5_0 | Expense Report: wrong employee name (Added By) — backend returns inconsistent names across endpoints | ¦ 2026-07-17 curl: profile.emp_f_name = expenses_report.employee_name = "Owner" ✓
BUG-091 | BUG | P2 |  | Closed (N/A) |  | pos_5_0 | CRM search API duplicates
CR-080 | CR | P3 |  | Closed (N/A) | 1 | pos_5_0_wave_3 | Transfer-First Smart Purchase — Franchise cross-flow optimisation (Phase 2 · depends on CR-077 + CR-078)
BUG-200 | BUG | ? | MEDIUM | Closed (N/A) | 1 | pos_5_0 | Expense Report — category filter returns 0 results (wrong query param name, needs curl verify) | Investigation 2026-07-17: 6 curl steps on cafe103 preprod. category_id=255 returns "To Owner" only. Date format DD/MM/YYYY confirmed. Report: evidence/BUG148_BUG200_INVESTIGATION_REPORT_2026_07_17.md
POS2-008 Phase 2 | CR | ? |  | Closed (N/A) |  | pos_5_0 | Backend-owned tone delivery | Backend owns implementation
BUG-097 | BUG | P1 |  | Other |  | pos_5_0 | Delivery dispatch + assign rider | Main flow SHIPPED. Bucket 5 (rider socket): RE-INVESTIGATE — owner says backend now emits. See BUG_097_BUCKET5_RIDER_SOCKET_EVENTS.md
BUG-163 | BUG | P1 | LOW | Other | 5b | pos_5_0 | CR-059 Setup — Export fails: missing type field in POST body | Excel export fix shipped in prior session but the entire export button was removed in CR-074-A (2026-07-16). Retained in registry as historical resolved record.
CR-011 | CR | P1 |  | Other | Phase 3 — Gate ①+④ COMPLETE for all 28 screens. Awaiting Gate ②③⑤⑥. | pos_5_0 | Complete Reports Module (new, role-based, separate tab) | Option C adopted 2026-06-01: template screens merge with first real exemplar (S2 = Aggregated Template + Item Sales). S2 wired against /order-logs-report + /get-products-list + /get-categories. Awaiti…
CR-053 | CR | P1 | HIGH | Other |  | pos_5_0 | MyGenie Training Academy — In-App Training & Mission System | Major feature. 3 phases, ~55-70 days. UX is #1 priority. Owner brainstormed extensively.
CR-065 | CR | P1 | MEDIUM | Other | 1 | pos_5_0 | Item-level inline edit (rename) on Expense Setup item list | Inline rename subset of BUG-202 (rename + change category with backend brief + snapshot/retroactive semantics locked). BUG-202 takes over.
CR-070 | CR | P1 | MEDIUM | Other | N/A | pos_5_0 | Role Management (Migration Phase 2 — Role CRUD + Permission Matrix)
CR-081 | CR | P1 | HIGH | Other |  | pos_5_0 | Inventory V5 Mockup Design Alignment Pass — 4 phases (Nav Tab Bar + Dashboard + Smart Purchase + Other Screens)
CR-117 | CR | P1 | LOW | Other | 5a | pos_5_0 | Order Report Beta — Combined Backend-Aggregated Daily Order Report | ¦ Backend delivered all 9 fields (confirmed 2026-08-01 probe). 6 tabs + 2 filters unblocked. Planning addendum written. Awaiting Gate 4 GO for unblocked scope. ¦ Gate 2 CLOSED 2026-08-01. Two restaur…
BUG-095 | BUG | P2 |  | Other |  | pos_5_0 | Socket handler + dead code cleanup | BUG-088+089 shipped. handleUpdateOrder dead code. Intake updated 2026-06-15.
BUG-139 | BUG | P2 | LOW | Other |  | pos_5_0 | Collapsed Sidebar — nested items inaccessible (auto-expand fix) | 1-line fix: auto-expand sidebar when clicking parent item in collapsed state. Sidebar.jsx L272.
BUG-172 | BUG | P2 | LOW | Other | 1 | pos_5_0 | ExpenseBulkEditor: "+ Add Row" in footer instead of "+ Add Item" in header — design inconsistency vs Menu Management | ExpenseBulkEditor "+ Add Row" vs "+ Add Item" design inconsistency. CR-074-B redesign supersedes; unified header pattern will be part of the Menu-Management-style refresh.
BUG-173 | BUG | P2 | MEDIUM | Other | 1 | pos_5_0 | ExpenseBulkEditor: Unit column displayed and collected but never sent to API — silently discarded (backend stock items have no unit field) | Unit column collected but never sent. Column set + payload wiring will be decided by CR-074-B design.
BUG-174 | BUG | P2 | MEDIUM | Other | 1 | pos_5_0 | ExpenseBulkEditor: Download Template button missing + STOCK_SAMPLE URL returns 404 on backend | Download Template feeds an Import feature that no longer exists after CR-074-A removed all bulk import/export. Template + STOCK_SAMPLE endpoint have no consumer.
CR-073-FU-01 | CR | P2 | MEDIUM | Other |  | pos_5_0 | Recipe Bulk Editor — Column Visibility Toggle (missing from CR-073 implementation)
BUG-094 | BUG | P3 |  | Other |  | pos_5_0 | Delivery-assign-order socket missing payload
CR-075 | CR | ? | HIGH | Other | 1 | pos_5_0 | Inventory Module UX Overhaul — Stock export fix, status chips, vendor typeahead, error display, field validation, Purchase/Receive conditional

## 🟡 Awaiting Smoke
Owner Smoke Required — 172 items (Awaiting Smoke + QA Passed)
ID | Type | Priority | Status | Title
BUG-138 | BUG | P0 | Awaiting Smoke | Discount Payload — order_discount and self_discount Wrong Values
BUG-158 | BUG | P0 | Awaiting Smoke | CR-059 Setup — Add Item to category silently fails (PUT ignores stock_title)
BUG-159 | BUG | P0 | Awaiting Smoke | CR-059 Setup — Add Category silently fails (empty stock_title → HTML redirect misread as 200)
BUG-168 | BUG | P0 | Awaiting Smoke | Bill print omits addons on dashboard/reports reprint (fallback subtotal loop misses add_ons[])
BUG-290 | BUG | P0 | Awaiting Smoke | Aggregator Manual Print fires to wrong restaurant — aggrId passed instead of orderId
BUG-VQTY | BUG | P0 | Awaiting Smoke | Variation quantity not multiplied by item qty in order/bill payloads
CR-082 | CR | P0 | Awaiting Smoke | Socket Room-Join — FE must emit join('rest_<rid>') after socket connect so room-scoped backend events reach the POS client
CR-097 | CR | P0 | Awaiting Smoke | Auto-Settle — Throttle/Stagger Concurrent Settle Calls on Dashboard Load
BUG-096 | BUG | P1 | Awaiting Smoke | Realtime FE updates for menu + hold/unpaid
BUG-130 | BUG | P1 | Awaiting Smoke | Channel Visibility: Restaurant Settings Channels Not Reflected in POS Dashboard
BUG-135 | BUG | P1 | Awaiting Smoke | Bulk Editor — Save errors: inactive status not persisting + error messages not surfacing backend description (3 sub-items)
BUG-144 | BUG | P1 | Awaiting Smoke | Token Number not on order tickets / not passed to print
BUG-150 | BUG | P1 | Awaiting Smoke | DnD item bounces back — categoryId null in expenses-list API + hidden placeholder
BUG-151 | BUG | P1 | Awaiting Smoke | Edit transaction fails — editRow.expense key ≠ data.exp_name in editExpenseEntry service
BUG-152 | BUG | P1 | Awaiting Smoke | Delete transaction fails — wrong endpoint (DELETE /edit-expense returns 405; correct: /delete-expense)
BUG-154 | BUG | P1 | Awaiting Smoke | Add expense: qty/price conditional logic — if item has unitPrice show qty + read-only calc amount; else hide qty
BUG-155 | BUG | P1 | Awaiting Smoke | Add expense: show optional category dropdown after free-text item entry (not for master items)
BUG-160 | BUG | P1 | Awaiting Smoke | CR-059 Setup — Rename Category broken (no rename endpoint on backend)
BUG-161 | BUG | P1 | Awaiting Smoke | CR-059 Setup — Bulk Save new items silently fails (PUT ignores stock_title)
BUG-167 | BUG | P1 | Awaiting Smoke | Menu socket (food_update channel) lost on non-dashboard routes — useSocketEvents only mounted in DashboardPage
BUG-194 | BUG | P1 | Awaiting Smoke | Payments report in Insights — completely empty / no data
BUG-195 | BUG | P1 | Awaiting Smoke | Takeaway Orders — Name mandatory toggle not working
BUG-280 | BUG | P1 | Awaiting Smoke | Customer Details Not Sent to Settle API from Collect Bill
BUG-281 | BUG | P1 | Awaiting Smoke | custGST/custGSTName Not Forwarded to Auto-Bill Print (4 Missing Sites)
BUG-282 | BUG | P1 | Awaiting Smoke | Aggregator Popup: Addons + Variations Not Displayed
BUG-286 | BUG | P1 | Awaiting Smoke | Aggregator KOT/Bill Buttons Hidden on OrderCard (canPrintBill Permission Gate)
BUG-288 | BUG | P1 | Awaiting Smoke | Menu Management: Station Dropdown Only Shows KDS (Other Stations Missing)
BUG-ROOM-PAIDROOM | BUG | P1 | Awaiting Smoke | paid_room field always empty on bill collection for room orders
CR-046 | CR | P1 | Awaiting Smoke | Control Dashboard v2.0 — Interactive Workflow Controller (login, batch queue, gate approvals, smoke cards)
CR-048 | CR | P1 | Awaiting Smoke | Auto-Sync Registry → Dashboard JSON (eliminate manual sync gap)
CR-049 | CR | P1 | Awaiting Smoke | Insights Module: Migrate FE Aggregation to Backend Aggregation Endpoints
CR-059 | CR | P1 | Awaiting Smoke | Expense Module — Migration from Old POS to New POS
CR-061 | CR | P1 | Awaiting Smoke | Expense Report — FE Build with Client-Side Aggregation
CR-067 | CR | P1 | Awaiting Smoke | Expense Bulk Editor — Full Parity Redesign with Menu Management Pattern
CR-118 | CR | P1 | Awaiting Smoke | Aggregator KOT & Bill Manual Print
CR-122 | CR | P1 | Awaiting Smoke | Inventory: Rename 'Smart Purchase' → 'Stock Update' + Move Vendor Preview to Top
BUG-092 | BUG | P2 | Awaiting Smoke | Phone format contract undefined for room check-in
BUG-136 | BUG | P2 | Awaiting Smoke | Sidebar scroll jumps to top on navigation (Sidebar re-mounts per page)
BUG-147 | BUG | P2 | Awaiting Smoke | Duplicate-item error toast doesn't include item name
BUG-153 | BUG | P2 | Awaiting Smoke | Add expense UX — category required blocks free-text entry; no cross-category item suggestions
BUG-156 | BUG | P2 | Awaiting Smoke | Add expense: default payment method should be Cash Draw (not empty)
BUG-157 | BUG | P2 | Awaiting Smoke | Expense Setup DnD: category pills too small — need bigger padding for 6-8 category usability
BUG-175 | BUG | P2 | Awaiting Smoke | Expense Entry Form Case A: qty input shown when item has unit price — should be hidden
BUG-176 | BUG | P2 | Awaiting Smoke | Expense Entry Form Case B: optional qty/unit/physical_qty hidden; physical_quantity wrongly deprecated
BUG-188 | BUG | P2 | Awaiting Smoke | Order screen — Discount section alignment issue
BUG-283 | BUG | P2 | Awaiting Smoke | Aggregator: 'Order Instructions :::' Prefix Not Stripped from Zomato Notes
BUG-284 | BUG | P2 | Awaiting Smoke | Aggregator: Address Shows Duplicate City ('Bangalore, Bangalore')
BUG-285 | BUG | P2 | Awaiting Smoke | Aggregator OrderCard: 'Ready to Dispatch' Should Be Text Label, Not Button
BUG-287 | BUG | P2 | Awaiting Smoke | Aggregator: 'This is order level instructions' Default Placeholder Not Stripped
BUG-289 | BUG | P2 | Awaiting Smoke | Restaurant Settings: Default Order Status Dropdown Has Wrong Labels (5 options incorrect)
CR-041 | CR | P2 | Awaiting Smoke | Sidebar Restructure: Reorder, Rename, Panel→Route Migration, Settings Consolidation
CR-045 | CR | P2 | Awaiting Smoke | Insights Module: Suppress/Ignore Unused API Response Fields (FE Strip)
CR-051 | CR | P2 | Awaiting Smoke | Customer Field Mandatoriness Override (Visibility Section)
CR-052 | CR | P2 | Awaiting Smoke | Sidebar Hover Flyout — collapsed sidebar shows popover with children on hover/click
CR-066 | CR | P2 | Awaiting Smoke | Unit Price Management: owner-only route for setting/editing expense stock item unit prices
CR-120 | CR | P2 | Awaiting Smoke | Aggregator: Split KOT/Bill Buttons by Order Status (Preparing→KOT, Ready→Bill)
CR-123 | CR | P2 | Awaiting Smoke | Stock Update: 'Update Stock' Button Sticky Fixed Bottom-Right
BUG-202 | BUG | ? | Awaiting Smoke | Expense Setup — no Edit Item (rename + change category) capability; DnD workaround unsafe
BUG-234 | BUG | ? | Awaiting Smoke | Employee Role Dropdown Shows System Roles + Silent ID Mismatch
BUG-235 | BUG | ? | Awaiting Smoke | Role Permissions Save Fails with 422 — role_type Empty on Create/Toggle
CR-096 | CR | ? | Awaiting Smoke | Role Type Derivation from Template map_role (Option A)
BUG-185 | BUG | P0 | QA Passed | Day Closure / Settlement — Opening balance logic not working correctly (INVESTIGATION)
BUG-206 | BUG | P0 | QA Passed | RecipeBulkEditor Batch Save fails — foodId null payload (BUG-197 #7 not ported to Bulk Editor)
BUG-164 | BUG | P1 | QA Passed | Add Category: duplicate name shows success toast instead of error
BUG-165 | BUG | P1 | QA Passed | Add Item: duplicate item name silently allowed — backend creates duplicate
BUG-179 | BUG | P1 | QA Passed | Expense Report: Excel export produces empty file — wrong argument shape to exportReportAsExcel
BUG-180 | BUG | P1 | QA Passed | Expense Report: PDF export throws error — wrong arguments to exportReportAsPDF (missing openReportWindow)
BUG-186 | BUG | P1 | QA Passed | Day Closure / Settlement — Unable to settle payment in Partial mode
BUG-203 | BUG | P1 | QA Passed | Unit price edit/add gaps across all expense contexts (4 sub-issues: A=Stock Master DONE, B=Bulk new row, C=Bulk edit silent fail, D=Edit expense qty/amount)
BUG-204 | BUG | P1 | QA Passed | Add Expense: priced items (Case A) hide qty input — amount locked to unitPrice×1, cannot enter quantity for multi-unit purchases
BUG-207 | BUG | P1 | QA Passed | RecipeBulkEditor Cost=₹0 Margin=100% — ingredient cost data not returned by recipe API
BUG-208 | BUG | P1 | QA Passed | Expense Bulk Edit price reverts after save + Unit Price removal UX gaps
BUG-210 | BUG | P1 | QA Passed | Dashboard Widget Data Calculation Errors — 4 fixes: Reorder Forecast negative-stock filter, Cost Trend 7d window too narrow, KPI ignores OOS items, rate missing units
BUG-240 | BUG | P1 | QA Passed | Smart Purchase: On-Hand Shows Small Unit (gm) Instead of Display Unit (kg)
BUG-241 | BUG | P1 | QA Passed | Smart Purchase: Rate Auto-Fills From Vendor History Making Unselected Items Active
BUG-242 | BUG | P1 | QA Passed | Smart Purchase: No Default Vendor + Allows Submit With Null Vendor
BUG-270 | BUG | P1 | QA Passed | Update Order Missing cust_mobile / cust_membership_id in update-place-order Payload
BUG-271 | BUG | P1 | QA Passed | GST/VAT Wrong on Print from Dashboard/Order Page (Manual Print Path Uses Proportional Split)
BUG-274 | BUG | P1 | QA Passed | Bulk Delete in Ingredient Bulk Editor Not Working — handleSave Early Return Blocks Delete Processing
BUG-277 | BUG | P1 | QA Passed | Ingredient Bulk Editor: Multi-Select Checkbox Resets on 2nd Row Click
BUG-278 | BUG | P1 | QA Passed | Ingredient Bulk Editor: DELETE API Called Twice Per Ingredient (400 Bad Request)
CR-060 | CR | P1 | QA Passed | Table/Room Management — Wire CRUD APIs to Existing UI
CR-069 | CR | P1 | QA Passed | Employee Management + Role Management (Migration Wave 1)
CR-072 | CR | P1 | QA Passed | Inventory Management — Migration from Old POS
CR-073 | CR | P1 | QA Passed | Recipe Bulk Editor — Inline Spreadsheet for Recipe Management (92+ recipes)
CR-077 | CR | P1 | QA Passed | Hierarchy Stock Transfer — Receive · Dispatch · Dispute · Return (split from CR-075 P5 per B15)
CR-078 | CR | P1 | QA Passed | Smart Purchase — Item-First Planner with Velocity & Vendor Intelligence (split from CR-075 per Q10-a)
CR-083 | CR | P1 | QA Passed | Expense Split/Partial Payment — split single expense across multiple payment methods (Cash+UPI, Paid+Unpaid)
CR-084 | CR | P1 | QA Passed | Vendor Management CRUD Screen — wire GET/PUT/DELETE vendor endpoints to VendorsTab. Replace vendor-types with actual vendor list.
CR-098 | CR | P1 | QA Passed | Short Code (Item Code) Display on Order Card
CR-099 | CR | P1 | QA Passed | Per-Item Preparation & Serve Time Display on Order Card
CR-102 | CR | P1 | QA Passed | Inventory Add/Edit: Send consumption_unit in Payload (G-020 Alignment)
CR-103 | CR | P1 | QA Passed | Smart Purchase: Bulk Remove UX (Select All + Prominent Cross Button)
CR-116 | CR | P1 | QA Passed | B2B Customer GST & Name Capture — New Input Fields in Collect Bill
BUG-162 | BUG | P2 | QA Passed | CR-059 Setup — Expense Setup panel flickers on every mutation (fetchAll full re-fetch pattern)
BUG-177 | BUG | P2 | QA Passed | Expense Entry: notes field missing from add form — backend accepts notes but FE form + payload omit it
BUG-178 | BUG | P2 | QA Passed | Expense Entry: item name editable via ItemCombobox in transaction edit — should be read-only
BUG-181 | BUG | P2 | QA Passed | Expense Entry: Added By column missing from daily transaction table — data available but not rendered
BUG-205 | BUG | P2 | QA Passed | Expense: Qty/Unit columns missing from transaction table + report
BUG-237 | BUG | P2 | QA Passed | Recipe Form — Recipe Name Field Should Be Hidden for Standard & Addon Types (Auto-Derived from Item Selection)
BUG-238 | BUG | P2 | QA Passed | Recipe Form — Replace Plain <select> Dropdowns with Searchable Combobox
BUG-239 | BUG | P2 | QA Passed | Recipe Form — Hide Serves Field for Sub-Recipe & Addon (Default 1)
BUG-272 | BUG | P2 | QA Passed | Partial Payment Breakdown Missing in Order Report (partial_payments Not Parsed)
BUG-275 | BUG | P2 | QA Passed | Edit Ingredient: Conversion Factor Pre-Fills to 1 When No Conversion Exists
BUG-276 | BUG | P2 | QA Passed | Bulk Editor UX: Category Move Causes Item Jump + Inconsistent Delete Between Expense/Ingredient Editors
BUG-279 | BUG | P2 | QA Passed | Ingredient Bulk Editor: Header Not Sticky on Scroll
CR-056 | CR | P2 | QA Passed | Restaurant Setting — toggle to show/suppress incoming scan-order popup
CR-062 | CR | P2 | QA Passed | Expense Report — Backend Aggregation Contract
CR-064 | CR | P2 | QA Passed | Add Item: include unit price field in quick-add form
CR-079 | CR | P2 | QA Passed | Inventory Information Architecture Restructure — Intelligence-as-Dashboard (split from CR-075 per FB-5)
CR-101 | CR | P2 | QA Passed | Daily Report — Collected By + Punched By Filter Dropdowns on Settled Tab
CR-107 | CR | P2 | QA Passed | Aggregator Auto-Accept (with Dynamic Prep Time)
CR-109 | CR | P2 | QA Passed | Dynamic Prep Time + Auto-Accept for Aggregator (no KOT/bill — separate CR)
CR-110 | CR | P2 | QA Passed | MyGenie Brand Badge for Own Delivery Orders
CR-111 | CR | P3 | QA Passed | OrderCard Aggregator Item Format: ● Qty× Name Pattern
CR-112 | CR | P3 | QA Passed | OrderCard Item Price Display (₹ per item line)
CR-113 | CR | P3 | QA Passed | OrderCard Customer+Phone Section for Aggregator
BUG-196 | BUG | ? | QA Passed | Sidebar missing on 6 inventory/employee pages
BUG-197 | BUG | ? | QA Passed | CR-072 Inventory Post-Delivery — 10 gaps (recipe CRUD, purchase Amount, vendor save, wastage CRUD, add ingredient, form validation)
BUG-198 | BUG | ? | QA Passed | CR-069 Employee Post-Delivery — 4 issues (update POST→PUT, add missing fields, reset password 3-bug stack, eye icon missing)
BUG-199 | BUG | ? | QA Passed | Expense Entry — new item always goes to misc category (categoryId not serialized to API payload)
BUG-201 | BUG | ? | QA Passed | Expense Deletion Safety — item + category cascade delete warning
BUG-211 | BUG | ? | QA Passed | Current Stock — No default sort (low stock buried) + KPI cards not clickable as filters
BUG-212 | BUG | ? | QA Passed | Ingredients — Edit missing (backend exists, FE unwired) + Add form incomplete (missing 4 fields) + Export button fake (toast only)
BUG-213 | BUG | ? | QA Passed | IngredientBulkEditor — Bulk Edit toolbar has no page title (G8 gap from CR-086 F4)
BUG-214 | BUG | ? | QA Passed | Addon Recipe Dropdown Shows Menu Items Instead of Addon Items
BUG-215 | BUG | ? | QA Passed | Recipe Forms — Validation Errors Not Shown on Save Failure
BUG-216 | BUG | ? | QA Passed | Recipe Ingredient Row Shows Base Unit, Should Show Small Unit
BUG-217 | BUG | ? | QA Passed | Sub-Recipe Serves Field Not Required But Blocks Save
BUG-218 | BUG | ? | QA Passed | Delete Ingredient — No Blocking Error When Used in Recipe
BUG-219 | BUG | ? | QA Passed | Ingredient Form — Min Unit Text Input, Factor/Min Q/Min U Labels Unclear
BUG-220 | BUG | ? | QA Passed | Ingredient Category — No Duplicate Alert, No Edit/Delete
BUG-221 | BUG | ? | QA Passed | Bulk Ingredient Upload & Excel Download Not Working
BUG-222 | BUG | ? | QA Passed | Bulk Recipe Excel — No Template/Export Split; File Won't Open
BUG-223 | BUG | ? | QA Passed | Wastage & Recipe Deduction Auto-Trigger Without Explicit Save
BUG-224 | BUG | ? | QA Passed | Smart Purchase — Ingredients Without Recipes Never Appear
BUG-226 | BUG | ? | QA Passed | Conversion Factor Not Saved on Add or Edit Ingredient
BUG-227 | BUG | ? | QA Passed | Smart Purchase — Vendor Column Shows No History Though Vendors Exist
BUG-229 | CR | ? | QA Passed | Employee: Auto-Populate Email (User ID) as firstname@restaurantname.com
BUG-230 | CR | ? | QA Passed | Employee: Name Change → Email Auto-Sync (if auto-generated)
BUG-231 | BUG | ? | QA Passed | Role Form: Hide role_type Field + Add Save Error Toasts
BUG-232 | BUG | ? | QA Passed | By Ingredient tab — empty combobox / no data on fast navigation (loading race)
BUG-244 | BUG | ? | QA Passed | add-purchase payload: wrong payment key + missing header totals
BUG-245 | BUG | ? | QA Passed | Table card moves to top when order placed (occupied-first bucketing)
BUG-246 | BUG | ? | QA Passed | Customized items not merging in cart (duplicate line items + print)
BUG-247 | BUG | ? | QA Passed | Smart Purchase ad-hoc typeahead blocks UI (perf — no React.memo)
BUG-248 | BUG | ? | QA Passed | Bulk Editor: 9 columns missing from isDirty — edits silently lost (Save never triggers)
BUG-249 | BUG | ? | QA Passed | Current Stock: Negative quantity items show "In Stock" badge — field mismatch (quantity vs displayQty)
BUG-258 | BUG | ? | QA Passed | P&L Report Calendar Broken / Different UI — No Presets, No Max Date
BUG-259 | BUG | ? | QA Passed | P&L Report Charts Hidden When ≤1 Data Point
BUG-260 | BUG | ? | QA Passed | Future Dates Allowed in 5 Report Calendars
BUG-261 | BUG | ? | QA Passed | Missing Preset Pills in P&L + Consumption Reports
BUG-262 | BUG | ? | QA Passed | Coming Soon Placeholders Visible in Production (6 Locations)
BUG-263 | BUG | ? | QA Passed | Smart Purchase — No Sticky Toolbar
BUG-264 | BUG | ? | QA Passed | System Vendor — No Explanation/Tooltip
BUG-265 | BUG | ? | QA Passed | Conversion Factor — No Help Text
BUG-269 | BUG | ? | QA Passed | Ingredient Add/Edit — 3 UX Bugs: Conversion Sent Incorrectly + No Small Unit Auto-Select + Alert Unit Not Read-Only
CR-074 | CR | ? | QA Passed | Expense Setup — remove Import/Export + design consistency refresh (match Menu Management)
CR-085 | CR | ? | QA Passed | Inventory Module Completion (Phase 2 Consolidation) — Design gaps, recipe backend blockers, unstarted features (Dispatch/S3/Column Toggle), code quality, registry sync
CR-086 | CR | ? | QA Passed | Current Stock & Ingredients UX Overhaul — Card-based filters, proper export fields, PDF export, Ingredient Bulk Editor, Import wiring
CR-087 | CR | ? | QA Passed | New Expense Payment Fields — payment_made_to + payment_ref_id
CR-088 | CR | ? | QA Passed | Recipe By Ingredient Reverse View Tab
CR-089 | CR | ? | QA Passed | PDF Export for Standard Sub and Addon Recipes
CR-090 | CR | ? | QA Passed | Inventory Categories — Edit and Delete
CR-092 | CR | ? | QA Passed | Recipe Tabs — Sort Controls
CR-093 | CR | ? | QA Passed | Consumption Report — New Screen (Date Range Category Ingredient Margin Cost)
CR-094 | CR | ? | QA Passed | P&L Report — New Screen Under Daily Reports Above Sales
CR-095 | CR | ? | QA Passed | Waiter-to-Waiter Transfer — Unlock Settlement Feature
CR-105 | CR | ? | QA Passed | Smart Purchase: Show All Ingredients + Manual Add to Purchase List
CR-114 | CR | ? | QA Passed | Smart Purchase — Default All Items Unselected (Opt-In)
CR-115 | CR | ? | QA Passed | Smart Purchase — Search Filter + Sort by Category
CR-125 | CR | ? | QA Passed | Aggregator Brand Name — Display on OrderCard + Include in Print Payload

## ⬜ Intake & Blocked
Needs Planning / Action — 34 items
ID | Type | Priority | Status | Title
BUG-123 | BUG | P1 | Plan Ready | Place Order on 401 silently redirects to dashboard; cashier mistakes failure for success
BUG-273 | BUG | P2 | Plan Ready | Auto Settle Local Settings Removal — Now Server-Side
BUG-225 | BUG | ? | Impact Done | Same Name Appears as Ingredient + Recipe; Unit Mismatch Across Screens
BUG-266 | BUG | ? | Impact Done | Wastage Report / Top Wasted Items — BACKEND-BLOCKED
BUG-118 | BUG | P1 | Intake | Nth-item coupon / BOGO coupon not working
BUG-183 | BUG | P1 | Intake | Daily Report — Phone number and customer name missing in Credit tab
BUG-184 | BUG | P1 | Intake | Daily Report — CRE-Credit payment type not reflecting in Payment column
BUG-189 | BUG | P1 | Intake | Delivery — Accept Order option missing for rider login (INVESTIGATION)
BUG-190 | BUG | P1 | Intake | Customer Notes not syncing with CRM / historical notes not showing (INVESTIGATION)
BUG-192 | BUG | P1 | Intake | Prep & Serve Time — Handover time showing 0 + full logic investigation
BUG-193 | BUG | P1 | Intake | Room Transfer Trail — showing table transfers + FROM ROOM showing 0 (INVESTIGATION)
CR-012 | CR | P1 | Intake | Menu Management — migrate to new API contract (scope-limited)
CR-057 | CR | P1 | Intake | Menu Management — add "No Tax" option + document tax rules
CR-058 | CR | P1 | Intake | Order-level "Mark Order Complimentary" action + mandatory discount note
CR-068 | CR | P1 | Intake | Cancellation role-gating — make cancellation rights role-based
CR-126 | CR | P1 | Intake | Backdated Billing Date — User-selectable billing date on order punch (backend-config gated)
BUG-124 | BUG | P2 | Intake | Backend food_update socket payload missing critical fields (status, is_disable, stock_out, food_status, live_web)
BUG-191 | BUG | P2 | Intake | Customer Intelligence — Phone number missing in Insights section
BUG-209 | BUG | P2 | Intake | Weight item qty display — Bill Summary missing unit labels (x100 instead of 100gm) + Receipt shows decimal Kg instead of gm
CR-043 | CR | P2 | Intake | Credit Per-Customer Totals in Reports + Portfolio Export Optimization
CR-121 | CR | P2 | Intake | Dashboard Quick-Start: Single-Click Order for Delivery / Takeaway / Walk-in
BUG-040 | BUG | P3 | Intake | Audit Report Excel / CSV Export Format Must Follow Provided Format
BUG-041 | BUG | P3 | Intake | Audit Report PDF Download — Mixed / Misaligned Rows, Logic Review & Refinement Needed
CR-050 | CR | P3 | Intake | Insights Dashboard: Quarterly Comparison View (Q1 vs Q2 revenue card)
POS2-001 | CR | ? | Intake | Delivery charge / GST / web delivery lock
BUG-243 | BUG | P0 | Blocked | Backend: Stock Not Credited After add-purchase (BACKEND-BLOCKED)
CR-100 | CR | P1 | Blocked | Smart Purchase — Partial Payment, Reference ID, Notes & Unpaid Status
BUG-090 | BUG | P2 | Blocked | CRM customer_id not stored on room orders
BUG-233 | BUG | ? | Blocked | By Ingredient tab: addon recipes never show — addon-recipe-list returns ingredients:[]
CR-091 | CR | ? | Blocked | Purchase — Transaction ID for Bank Transfer
CR-104 | CR | ? | Blocked | Item-level complementary reason (mandatory note per food item)
BUG-236 | BUG | P1 | Investigation | Smart Purchase — Ad-hoc Typeahead Dropdown Clipped by overflow-hidden
BUG-267 | BUG | ? | Investigation | Inventory Setup — Category Not Selecting When Adding Ingredient
BUG-268 | BUG | ? | Investigation | Inventory Setup — Edit Ingredient Fails: inventory_audit_logs.id Missing AUTO_INCREMENT