## Change Requests
ID | Title | Area | Priority | Risk | Status | Date Registered | Date Implemented | Sprint | Blocked | Notes
CR-357 | Room Advance — Full-Bill Deduction + Mid-Stay Deposits + Credit Overflow | PMS | P2 | HIGH | Parked | 2026-09-14 |  | pos_5_1 | No | Room Advance — Full-Bill Deduction + Mid-Stay Deposits + Credit Overflow
CR-358 | PMS Module — Property Management + Channel Manager Integration (AIOSELL + Room R | PMS | P1 | HIGH | Gate 3 — Implementation Plan |  |  | pos_5_2 | No | PMS Module — Property Management + Channel Manager Integration (AIOSELL + Room Redesign)
CR-358-P1 | PMS Phase 1 — Foundation + Channel Manager (S8) + In-House Guests (S6) | PMS | — | — | Gate 5b — QA Pass |  |  | pos_pms_1 | No | PMS Phase 1 — Foundation + Channel Manager (S8) + In-House Guests (S6)
CR-358-P2 | PMS Phase 2 — New Booking (S3) + Check-In (S4): WalkIn / Direct / OTA | PMS | P1 | MEDIUM | Gate 5b — QA Pass |  |  | pos_pms_1 | No | PMS Phase 2 — New Booking (S3) + Check-In (S4): WalkIn / Direct / OTA
CR-358-P3 | PMS Phase 3 — Reservation Operations: Front Desk (S1) + Arrivals (S9) + Departur | PMS | P1 | HIGH | Gate 6 — Owner Smoke | 2026-09-03 |  | pos_pms_1 | No | PMS Phase 3 — Reservation Operations: Front Desk (S1) + Arrivals (S9) + Departures (S10)
CR-358-P4 | PMS Phase 4 — Tape Chart (S2) + Room Status Board (S7) | PMS | P0 | MEDIUM | Gate 6 — Owner Smoke | 2026-09-04 | 2026-09-04 | — | No | PMS Phase 4 — Tape Chart (S2) + Room Status Board (S7)
CR-358-P5 | PMS Phase 5 — Rates & Restrictions tab (S8-C) + Mark No-Show (S8-D) + module reg | PMS | P1 | HIGH | Gate 6 — Owner Smoke | 2026-09-04 |  | pos_pms_1 | No | PMS Phase 5 — Rates & Restrictions tab (S8-C) + Mark No-Show (S8-D) + module regression
CR-358-P5.1 | PMS Phase 5.1 — Inventory Restrictions + Rate Restrictions (S8-C remainder) | PMS | P1 | HIGH | Closed | 2026-09-08 |  | pos_pms_1 | No | PMS Phase 5.1 — Inventory Restrictions + Rate Restrictions (S8-C remainder)
CR-359 | Station Mapping Tab: Rewire to /station-printer-map Endpoint + Fix Data Model | PMS | P1 | CRITICAL | Gate 6 — Owner Smoke |  |  | pos_5_x | No | Station Mapping Tab: Rewire to /station-printer-map Endpoint + Fix Data Model
CR-360 | S6 In-House Guests — Phase 1 completion: KPI tiles (Checkout Today / Outstanding | PMS | — | — | Gate 5b — QA Pass |  |  | pos_pms_1 | No | S6 In-House Guests — Phase 1 completion: KPI tiles (Checkout Today / Outstanding Balance /
CR-361 | PMS — Room Assignment on Tape Chart (pre-arrival mapping to physical rooms) | PMS | P1 | MEDIUM | Backend Blocked | 2026-09-04 |  | pos_pms_1 | Yes | PMS — Room Assignment on Tape Chart (pre-arrival mapping to physical rooms)
CR-362 | PMS — Booking Modification & Cancellation (cancel / modify dates-room / extend s | PMS | P1 | CRITICAL | Gate 6 — Owner Smoke | 2026-09-04 |  | pos_pms_1 | Yes | PMS — Booking Modification & Cancellation (cancel / modify dates-room / extend stay / no-s
CR-363 | PMS — Night Audit Report (end-of-day room reconciliation) | PMS | P1 | HIGH | Gate 5a — Implemented | 2026-09-04 | 2026-09-14 | pos_pms_1 | No | PMS — Night Audit Report (end-of-day room reconciliation)
CR-364 | PMS — Guest Folio Detail Page (itemised charges, payments, balance, checkout) | PMS | P1 | HIGH | Gate 5a — Implemented | 2026-09-04 | 2026-09-14 | pos_pms_1 | No | PMS — Guest Folio Detail Page (itemised charges, payments, balance, checkout)
CR-364-PRINT | PMS — Guest Folio Print Template (rtype=RM branch, ~60-field payload extension) | PMS | P2 | HIGH | Parked | 2026-09-14 |  | pos_pms_1 | Yes | PMS — Guest Folio Print Template (rtype=RM branch, ~60-field payload extension)
CR-365 | PMS — Housekeeping Workflow (task queue, checklist, assignment, time tracking, n | PMS | P2 | MEDIUM | Gate 2 — Impact Analysis | 2026-09-04 |  | pos_pms_1 | No | PMS — Housekeeping Workflow (task queue, checklist, assignment, time tracking, notificatio
CR-366 | PMS — Revenue Dashboard / Analytics (Occupancy %, ADR, RevPAR, channel split, tr | PMS | P2 | MEDIUM | Gate 5a — Implemented | 2026-09-04 | 2026-09-14 | pos_pms_1 | No | PMS — Revenue Dashboard / Analytics (Occupancy %, ADR, RevPAR, channel split, trends)
CR-367 | PMS — WhatsApp / SMS Guest Notifications (confirmation, check-in instructions, c | PMS | P2 | HIGH | Backend Blocked | 2026-09-04 |  | pos_pms_1 | Yes | PMS — WhatsApp / SMS Guest Notifications (confirmation, check-in instructions, checkout re
CR-368 | Test Suite Triage — Achieve Zero-Failure Baseline | POS | P1 | MEDIUM | Gate 2 — Impact Analysis | 2026-09-08 |  | pos_audit_1 | No | Test Suite Triage — Achieve Zero-Failure Baseline
CR-369 | Write AGENT_PROMPT_ALPHA_v0.8.md | POS | P1 | LOW | Intake | 2026-09-08 |  | pos_audit_1 | No | Write AGENT_PROMPT_ALPHA_v0.8.md
CR-370 | Stale Doc Corrections — 5 Records from Audit §3 | POS | P2 | LOW | Gate 5a — Implemented | 2026-09-08 | 2026-09-08 | pos_audit_1 | No | Stale Doc Corrections — 5 Records from Audit §3
CR-371 | Build sync_registry.py — Canonical Registry Sync Script | POS | P1 | LOW | Intake | 2026-09-08 |  | pos_audit_1 | No | Build sync_registry.py — Canonical Registry Sync Script
CR-372 | Security Remediation — Remove Internal Files from Public Surface | POS | P1 | HIGH | Intake | 2026-09-08 |  | pos_audit_1 | No | Security Remediation — Remove Internal Files from Public Surface
CR-372-A | Security: File Moves + .env Cleanup (Zero src/ changes) | POS | P1 | LOW | Gate 5a — Implemented | 2026-09-08 |  | pos_audit_1 | No | Security: File Moves + .env Cleanup (Zero src/ changes)
CR-372-B | Security: Add ProtectedRoute to 23 Unguarded Routes (App.js only) | POS | P1 | MEDIUM | Intake | 2026-09-08 |  | pos_audit_1 | No | Security: Add ProtectedRoute to 23 Unguarded Routes (App.js only)
CR-373 | Aggregator ProductForm: Use Item Image for Swiggy toggle | POS | — | LOW-MEDIUM | Gate 5a — Implemented |  |  | pos_7_0 | No | Aggregator ProductForm: Use Item Image for Swiggy toggle
CR-374 | BulkEditor Filter Panel — Status / Type / Category (Always-Visible Strip) | POS | — | MEDIUM | Gate 5a — Implemented |  |  | pos_7_0 | No | BulkEditor Filter Panel — Status / Type / Category (Always-Visible Strip)
CR-375 | Aggregator Menu: Bulk Delete Capability in BulkEditor | POS | — | MEDIUM | Intake |  |  | pos_7_0 | No | Aggregator Menu: Bulk Delete Capability in BulkEditor
CR-376 | POS Order Entry: Menu Switch (Normal / Party / Premium tabs) | POS | — | MEDIUM | Gate 4 — GO |  |  | pos_7_0 | No | POS Order Entry: Menu Switch (Normal / Party / Premium tabs)
CR-377 | Sales Report Complete Redesign — surface all 82 API fields (Expense, Purchase, G | POS | P2 | MEDIUM | Gate 5a — Implemented |  |  | pos_7_0 | No | Sales Report Complete Redesign — surface all 82 API fields (Expense, Purchase, Galla/Cash
CR-378 | Sidebar Profile — Show Restaurant Name Alongside Restaurant ID | PMS | P2 | LOW | Gate 6 — Owner Smoke | 2026-09-11 |  | pos_7_0 | No | Sidebar Profile — Show Restaurant Name Alongside Restaurant ID
CR-379 | New PMS Check-In: CRM Customer Link (Core) | PMS | P1 | HIGH | Gate 5b — QA Pass |  |  | pos_pms_1 | No | New PMS Check-In: CRM Customer Link (Core)
CR-380 | New PMS Check-In: Guest ID Documents | PMS | P1 | HIGH | Gate 5b — QA Pass |  |  | pos_pms_1 | No | New PMS Check-In: Guest ID Documents
CR-381 | PMS — Laundry Management (linen queue, stock levels, dirty→clean processing, set | PMS | — | MEDIUM | Gate 2 — Impact Analysis | 2026-09-16 |  | pos_pms_1 | No | PMS — Laundry Management (linen queue, stock levels, dirty→clean processing, settings)

## Bugs
ID | Title | Area | Priority | Risk | Status | Date Registered | Date Implemented | QA Status | Owner Smoke | Notes
BUG-193 | Room Transfer Trail — showing table transfers + FROM ROOM showing 0 (INVESTIGATION) | PMS | P1 | MEDIUM | Intake |  |  | — | — | Room Transfer Trail — showing table transfers + FROM ROOM showing 0 (INVESTIGATION)
BUG-368 | Split Bill by Payment — settled order cannot be reprinted from Order Report | POS | P1 | HIGH | Gate 5a — Implemented | 2026-09-01 |  | QA Pending | — | Split Bill by Payment — settled order cannot be reprinted from Order Report
BUG-369 | Print Customer Copy setting enabled but no separate customer bill is printed | POS | P1 | MEDIUM | Gate 5a — Implemented | 2026-09-01 |  | QA Pending | — | Print Customer Copy setting enabled but no separate customer bill is printed
BUG-370 | Delivery order: Reassign option missing when status is Waiting for Rider | POS | P2 | LOW | Gate 6 — Owner Smoke | 2026-09-01 |  | QA Pass | Done | Delivery order: Reassign option missing when status is Waiting for Rider
BUG-371 | Bulk Editor — variation price not editable (read-only, no price input in expand panel | POS | P2 | MEDIUM | Gate 5a — Implemented | 2026-09-01 |  | QA Pending | — | Bulk Editor — variation price not editable (read-only, no price input in expand panel)
BUG-372 | Transfer and Merge buttons on order card not working from outside Order Entry view | POS | P1 | HIGH | Gate 5a — Implemented | 2026-09-01 |  | QA Pending | — | Transfer and Merge buttons on order card not working from outside Order Entry view
BUG-373 | Service Charge label hardcoded — custom label from settings ignored in UI and Printer | POS | P2 | MEDIUM | Gate 6 — Owner Smoke | 2026-09-01 |  | QA Pass | Done | Service Charge label hardcoded — custom label from settings ignored in UI and Printer Agen
BUG-374 | Cart: Increasing quantity of one variation (30ml) also changes the other variation (6 | POS | P0 | CRITICAL | Gate 5a — Implemented | 2026-09-01 |  | QA Pending | — | Cart: Increasing quantity of one variation (30ml) also changes the other variation (60ml)
BUG-375 | Normal Menu Management shows Zomato Image field — should only show for aggregator-ena | POS | P3 | LOW | Gate 6 — Owner Smoke | 2026-09-01 |  | QA Pass | Done | Normal Menu Management shows Zomato Image field — should only show for aggregator-enabled
BUG-376 | Role Add/Update: 5 API Contract Gaps (modules prefix · role_master_id null · role_typ | POS | P1 | HIGH | Gate 5a — Implemented |  |  | QA Pending | — | Role Add/Update: 5 API Contract Gaps (modules prefix · role_master_id null · role_type IDs
BUG-377 | PMS Room Mapping: dropdown shows Unassigned despite Mapped status | PMS | — | — | Gate 5a — Implemented |  |  | QA Pending | — | PMS Room Mapping: dropdown shows Unassigned despite Mapped status
BUG-378 | PMS In-House Guests: Room/Phone/Dates/Balance all show dash | PMS | — | — | Gate 5a — Implemented |  |  | QA Pending | — | PMS In-House Guests: Room/Phone/Dates/Balance all show dash
BUG-379 | Stock Audit save fails 422 — toAPI.addStock() missing unit + physical_qty + physicalq | PMS | P1 | MEDIUM | Gate 5b — QA Pass |  |  | QA Pass | Pending | Stock Audit save fails 422 — toAPI.addStock() missing unit + physical_qty + physicalqty_ma
BUG-380 | Occupied rooms shown in New Booking room picker — double-booking possible | PMS | P1 | HIGH | Gate 6 — Owner Smoke |  |  | QA Pass | Done | Occupied rooms shown in New Booking room picker — double-booking possible
BUG-381 | Walk-in check-in guest data missing on In-House + P3 PMS pages | PMS | P1 | HIGH | Gate 6 — Owner Smoke |  |  | QA Pass | Done | Walk-in check-in guest data missing on In-House + P3 PMS pages
BUG-383 | RoomStatusPage HK filter count always 0 — manual_status vs displayStatus mismatch | PMS | P1 | MEDIUM | Gate 5b — QA Pass | 2026-09-08 |  | QA Pass | Pending | RoomStatusPage HK filter count always 0 — manual_status vs displayStatus mismatch
BUG-384 | POST room-payment returns HTTP 403 — sandbox-pms owner role permission gap | PMS | P1 | HIGH | Closed | 2026-09-08 |  | QA Pass | Done | POST room-payment returns HTTP 403 — sandbox-pms owner role permission gap
BUG-385 | no_show field absent from local-reservations and dashboard-kpis — blocks CR-363 Night | PMS | P2 | LOW | Closed | 2026-09-08 |  | QA Pass | Done | no_show field absent from local-reservations and dashboard-kpis — blocks CR-363 Night Audi
BUG-386 | PMS Check-In: Room Accommodation GST Never Computed or Sent (gst_tax Hardcoded 0.00) | PMS | — | CRITICAL | Gate 6 — Owner Smoke |  |  | QA Pass | Done | PMS Check-In: Room Accommodation GST Never Computed or Sent (gst_tax Hardcoded 0.00)
BUG-387 | PMS Picker: HK and OOO Rooms Appear Selectable in Check-In / New Booking | PMS | — | HIGH | Gate 6 — Owner Smoke |  |  | QA Pass | Done | PMS Picker: HK and OOO Rooms Appear Selectable in Check-In / New Booking
BUG-388 | PMS Check-In: Advance payment excluded from GST base — wrong slab, wrong balance_paym | PMS | — | — | Gate 6 — Owner Smoke |  |  | QA Pass | Done | PMS Check-In: Advance payment excluded from GST base — wrong slab, wrong balance_payment
BUG-389 | PMS Room GST: slab2.min=7500.01 causes ₹7,500 exact to hit 5% slab (should be 18%) | PMS | — | — | Backend Blocked |  |  | — | — | PMS Room GST: slab2.min=7500.01 causes ₹7,500 exact to hit 5% slab (should be 18%)
BUG-390 | Normal Menu Image Upload Hidden — Aggregator gate regression from BUG-375 | POS | — | LOW | Gate 5a — Implemented |  |  | QA Pending | — | Normal Menu Image Upload Hidden — Aggregator gate regression from BUG-375
BUG-391 | Aggregator Menu: GST Not Enforced — Items Saveable With 0% Tax or None Tax Type | POS | — | HIGH | Gate 5a — Implemented |  |  | QA Pending | — | Aggregator Menu: GST Not Enforced — Items Saveable With 0% Tax or None Tax Type
BUG-392 | All Number Inputs Respond to Scroll Wheel — Accidental Price/Tax/Charge Changes in Me | POS | — | LOW | Gate 5a — Implemented |  |  | QA Pending | — | All Number Inputs Respond to Scroll Wheel — Accidental Price/Tax/Charge Changes in Menu Ma
BUG-393 | Daily Sales Report: getDailySalesReport missing 'to' field in POST payload | POS | P2 | LOW | Closed |  |  | QA Pass | Done | Daily Sales Report: getDailySalesReport missing 'to' field in POST payload
BUG-394 | Number inputs: special chars corrupt data + zero not cleared on focus (4 files) | POS | P1 | HIGH | Gate 5a — Implemented |  |  | QA Pending | — | Number inputs: special chars corrupt data + zero not cleared on focus (4 files)
BUG-395 | buildBillPrintPayload missing 4 delivery address sub-fields (house/floor/city/state) | POS | P2 | MEDIUM | Gate 5a — Implemented |  |  | QA Pending | — | buildBillPrintPayload missing 4 delivery address sub-fields (house/floor/city/state)
BUG-396 | PMS Check-In: GST calculated on advance payment (advance is deposit, not additional c | PMS | — | CRITICAL | Gate 6 — Owner Smoke |  |  | QA Pass | Done | PMS Check-In: GST calculated on advance payment (advance is deposit, not additional charge
BUG-397 | Room Status Board: occupied_hk display_status not handled — silently maps to availabl | PMS | — | HIGH | Gate 6 — Owner Smoke |  |  | QA Pass | Done | Room Status Board: occupied_hk display_status not handled — silently maps to available
BUG-398 | CR-163 Move Items: Path B Create-Room row hidden — missing roomNo fallback to table.t | PMS | — | HIGH | Gate 6 — Owner Smoke |  |  | QA Pass | Done | CR-163 Move Items: Path B Create-Room row hidden — missing roomNo fallback to table.tableN
BUG-399 | CR-163 Path B: area created + table persists + no refresh — Option A walk-in fix | PMS | — | HIGH | Gate 6 — Owner Smoke |  |  | QA Pass | Done | CR-163 Path B: area created + table persists + no refresh — Option A walk-in fix