## Bug Report Aug 7–14 2026
MyGenie POS — Bug Report ¦ 7 Aug 2026 → 14 Aug 2026
Source: /app/memory/control/BUG_TRACKER.md · Total bugs: 25
Bug ID | Date | Priority | Description | Status
BUG-SCAN-DEDUP | 2026-08-08 | P1 | show_scan_popup loads wrong value & save silently lost — backend dedup (2026-08-08) moved field from advanced{} to basic{}; FE still read/wrote advanced.show_scan_popup | IMPLEMENTED
BUG-303 | 2026-08-11 | P2 | P&L Report — 'Paid Revenue' KPI always shows ₹0 (field mismatch: s.paid_revenue vs s.total_paid_revenue in PLReportPage.jsx) | IMPLEMENTED — QA PASS
BUG-304 | 2026-08-11 | P1 | Item-Level Discount — discountRatio uses full itemTotal (not discountableTotal), causing wrong GST/VAT for non-discountable items (CollectPaymentPanel.jsx + CartPanel.jsx) | IMPLEMENTED — QA PASS
BUG-305 | 2026-08-11 | P1 | orderTransform.js — discountRatio uses full subtotal in calcOrderTotals + buildBillPrintPayload; wrong GST sent to backend payload and bill print (CRITICAL risk) | IMPLEMENTED — QA PASS
BUG-306 | 2026-08-11 | P1 | Aggregator Setup shows 'Network Error' / blank screen when GET /aggregator-config returns ERR_NETWORK (AggregatorSetupView.jsx isNoConfig guard missing) | IMPLEMENTED — QA PASS
BUG-307 | 2026-08-11 | P1 | Aggregator Setup: tone_timing (notification duration seconds) not mapped in UI — field missing from aggregatorConfigTransform.js fromAPI/toAPI + ConfigTab.jsx | IMPLEMENTED — QA PASS
BUG-296 | 2026-08-12 | P1 | Food Court Report vs Item-Wise Report — Revenue data mismatch (rid=598, Shimla QoH Food Court, June 2026). Two root causes: wrong sort_by field (created_at→collect_bill) + foodStatus=3 items not excluded (foodCourtService.js) | IMPLEMENTED — QA PASS
BUG-PL-A | 2026-08-12 | P1 | P&L Report — API returns all-zeros because reportService.js sends date_from/date_to but endpoint expects from/to parameter keys | IMPLEMENTED
BUG-PL-B | 2026-08-12 | P2 | P&L Report — API returns comma-formatted number strings (e.g. '537,876.02'); parseFloat() truncates at comma → KPI values cut off (reportService.js / PLReportPage.jsx) | IMPLEMENTED
BUG-308 | 2026-08-13 | P1 | Sub-Recipe Stock: StockAuditPanel calls addStock() (ingredient endpoint) instead of addSubRecipeStock() for sub-recipe entries — wrong API, wrong payload (constants.js + inventoryTransform.js + inventoryService.js + StockAuditPanel.jsx) | IMPLEMENTED
BUG-309 | 2026-08-13 | P1 | Ingredient Bulk Edit: Min Unit column uses <input type=number> which drops the unit string on save — data loss on every save (IngredientBulkEditor.jsx:442 input→span) | IMPLEMENTED
BUG-310 | 2026-08-13 | P2 | Ingredient Bulk Edit: Conversion Factor field has transparent border/background (numCls false) — looks like static text, users cannot tell it is editable (IngredientBulkEditor.jsx:296) | IMPLEMENTED
BUG-311 | 2026-08-13 | P1 | Ingredient Add / Bulk Edit: No duplicate detection at any layer — missing typeahead L1 (position:fixed dropdown in InventorySetupPanel.jsx:23), pre-save isDuplicate guard L2 (InventorySetupPanel.jsx:146), bulk-editor dupe skip L3 (IngredientBulkEditor.jsx:192) | IMPLEMENTED
BUG-312 | 2026-08-13 | P1 | fromAPI.ingredients() missing isSubRecipe/subrecipeId fields — root cause for all sub-recipe misrouting throughout inventory transforms (inventoryTransform.js fromAPI.ingredients()) | SUBSUMED (Implemented via CR-139)
BUG-313 | 2026-08-13 | P1 | Sub-recipe rows appear in Stock Update auto-plan + addPurchase() called for all rows with no sub-recipe routing guard (purchasePlanner.js, AutoShoppingList.jsx, PurchaseEntryPanel.jsx, SmartPurchasePanel.jsx) | SUBSUMED (Implemented via CR-139)
BUG-314 | 2026-08-13 | P1 | Inventory Setup: Categories (0) + Unit dropdown empty — Promise.all atomic failure when get-inventory-master returns 404; categories and units never set (InventorySetupPanel.jsx:42 → Promise.allSettled fix) | IMPLEMENTED
BUG-315 | 2026-08-13 | P2 | Printer Config: Numeric inputs snap-back — cannot clear '1' to retype value; controlled input returns '' early → React reverts (StyleInput in PrintStyleTab.jsx + NumberInput in shared.jsx → local display state fix) | IMPLEMENTED
BUG-316 | 2026-08-13 | P1 | Printer Config: Font Family dropdown empty because available_fonts is null from API — printerAgentConfigTransform.js:253 had no fallback; fix: FALLBACK_FONTS constant with 11 approved fonts | IMPLEMENTED
BUG-317 | 2026-08-13 | P2 | Printer Config: Android size fields (Logo/UPI/FeedbackQR) reject values >8 due to max=8 constraint inherited from CR-133 [1,8] default range — PrintStyleTab.jsx maxScale removed | IMPLEMENTED
BUG-318 | 2026-08-13 | P1 | Printer Config: Aggregator auto-print keys (auto_kot/auto_bill/auto_stage) missing from AutoPrintTab UI + saves to wrong API endpoint; CR-133 OD-B misrouted these — owner reversed OD-B; AutoPrintTab.jsx full rewrite + FALLBACK_AGGREGATOR_STAGES added | IMPLEMENTED
BUG-319 | 2026-08-13 | P2 | Printer Config: Footer text 'Powered by MyGenie' hardcoded in print agent firmware — API returns bill_footer.footer_text correctly but physical print agent ignores it; backend firmware change required | BACKEND-BLOCKED
BUG-320 | 2026-08-13 | P2 | Sub-Recipe Stock: physical_qty incorrectly included in add-sub-recipe-stock payload — physical_qty is an ingredient audit concept not applicable to sub-recipe produced-qty; always mirrored quantity (SubRecipeStockPanel.jsx:94 + inventoryTransform.js:227) | IMPLEMENTED
BUG-236 | 2026-08-14 | P1 | Smart Purchase — Ad-hoc Typeahead Dropdown clipped by overflow-hidden on Section 1 card; z-index too low (z-10→z-50). Fix: removed overflow-hidden from card (L130) + z-50 on both dropdown divs (L42, L47) in AdHocTypeahead (SmartPurchasePanel.jsx) | IMPLEMENTED
BUG-321 | 2026-08-14 | P1 | Sub-Recipe Stock Panel — Wrong Produce/Recount semantics: every save adds qty (ADD mode) but UI shows drift/wastage screen; StockAuditPanel.jsx:71 physicalQty=qty causes spurious wastage. Fix: mode toggle (Produce/Recount) + conditional physical_qty in transform + StockAuditPanel routing (3 files) | GATE 3 COMPLETE — Awaiting Gate 4 GO
BUG-322 | 2026-08-14 | P1 | Recipe Form — SearchableSelect ingredient dropdown clipped by overflow-hidden on table container (RecipeFormPanel.jsx:305); position:absolute dropdown hidden behind table. Fix: position:fixed + getBoundingClientRect on trigger. All recipe types affected (standard/sub/addon ingredient rows). Related: BUG-236, BUG-238 | IMPLEMENTED
Legend — Status Colors
IMPLEMENTED / QA PASS
BACKEND-BLOCKED
GATE 3 COMPLETE — Awaiting Gate 4
SUBSUMED (Implemented via CR-139)